## Version Control
Document Information
Title | Test Execution Log
Title | March Release
Release Identifier | RLSE0010182, RLSE0010184
Author
Document Version History
Version | Date | Summary of Changes
0.1 | 2026-02-03 | Draft RLSE0010182
0.2 | 2026-02-05 | Working Copy - RLSE0010184 added
0.3 | 2026-02-12 | Post peer review
0.4 | 2026-03-13 | Post MoJ Test Assurance review
Test Evidence Repository
Test Execution Evidence is stored at this link
Scope of Release
This release implements a Servicenow upgrade
Defect/Story ID | Type | Details

## Summary
|  |  | Phase 6 DASHBOARD |  |  |  | Variations DASHBOARD |  |  |  | OVERALL DASHBOARD
Execution Progress |  |  |  | Execution Progress |  |  |  | Execution Progress
Steps Completed | 164 |  |  | Steps Completed | 95 |  |  | Steps Completed | 0
Steps Remaining | 0 |  |  | Steps Remaining | 0 |  |  | Steps Remaining | 0
Total Steps | 164 |  |  | Total Steps | 95 |  |  | Total Steps | 0
% Complete | 100% |  |  | % Complete | 100% |  |  | % Complete | #DIV/0!
Script Status |  |  |  | Script Status |  |  |  | Script Status
Pass | 23 | 100% |  | Pass | 19 | 100% |  | Pass | 0 | #DIV/0!
Fail | 0 | 0% |  | Fail | 0 | 0% |  | Fail | 0 | #DIV/0!
No Run | 0 | 0% |  | No Run | 0 | 0% |  | No Run | 0 | #DIV/0!
Not Completed | 0 | 0% |  | Not Completed | 0 | 0% |  | Not Completed | 0 | #DIV/0!
In Progress | 0 | 0% |  | In Progress | 0 | 0% |  | In Progress | 0 | #DIV/0!
Out of Scope | 0 | 0% |  | Out of Scope | 0 | 0% |  | Out of Scope | 0 | #DIV/0!
Not Started | 0 | 0% |  | Not Started | 0 | 0% |  | Not Started | 0 | #DIV/0!
TOTAL | 23 |  |  | TOTAL | 19 |  |  | TOTAL | 0
|  |  | Acquisitive Crime DASHBOARD |  |  | Phase 7 DASHBOARD
Execution Progress |  |  |  | Execution Progress
Steps Completed | 125 |  |  | Steps Completed | 122
Steps Remaining | 0 |  |  | Steps Remaining | 0
Total Steps | 125 |  |  | Total Steps | 122
% Complete | 100% |  |  | % Complete | 100%
Script Status |  |  |  | Script Status
Pass | 13 | 100% |  | Pass | 11 | 100% |  |  |  | on you
Fail | 0 | 0% |  | Fail | 0 | 0%
No Run | 0 | 0% |  | No Run | 0 | 0%
Not Completed | 0 | 0% |  | Not Completed | 0 | 0%
In Progress | 0 | 0% |  | In Progress | 0 | 0%
Out of Scope | 0 | 0% |  | Out of Scope | 0 | 0%
Not Started | 0 | 0% |  | Not Started | 0 | 0%
TOTAL | 13 |  |  | TOTAL | 11

## Phase A
Test ID | Story | Requirements being tested | Pre-Requisites | Test Assurance Steps | Test Assurance Expected Outcome | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Execution Notes | Data notes | Reviewed by | Story
EX01 | STRY1000001 | Verify extraction of single Test IDs from specification | Data seeded; user access configured | 1. Open spec 2. Parse IDs 3. Validate count | EX01 detected and mapped to STRY1000001 | [5 empty] | Pass
EX02 | STRY1000001 | Verify continued extraction across adjacent rows | As above | 1. Continue parse 2. Validate sequence | EX02 detected and ordered correctly | [5 empty] | Pass
EX03 | STRY1000001 | Verify termination of extraction at section boundary | As above | 1. Detect boundary 2. Stop extraction | No bleed into next section | [5 empty] | Pass

## Phase B
Test ID | Story | Requirements being tested | Pre-Requisites | Test Assurance Steps | Test Assurance Expected Outcome | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Execution Notes | Data notes | Reviewed by | Story
EX10 | STRY1000002 | Verify multi-sheet extraction capability | Workbook available | 1. Load workbook 2. Iterate sheets 3. Aggregate IDs | IDs collected from multiple sheets | [5 empty] | Pass
EX11 | STRY1000002 | Verify sheet filtering (ignore Summary/Validation) | Workbook includes non-data sheets | 1. Apply filter 2. Skip ignored sheets | Only data sheets processed | [5 empty] | Pass
EX12 | STRY1000002 | Verify consistent parsing across sheets | As above | 1. Parse both sheets 2. Compare schemas | Consistent column mapping | [5 empty] | Pass
EX20 | STRY1000003 | Verify cross-sheet reuse of Test IDs | As above | 1. Identify duplicates 2. Map to stories | Reuse correctly attributed | [5 empty] | Pass
EX21 | STRY1000003 | Verify deduplication rules | As above | 1. Apply dedupe 2. Validate output | No duplicate inflation | [5 empty] | Pass

## Defects
Incident / JIRA ref | Test ID | Issue | Description | Category | Impact Rating (H-M-L) | Date Opened | Date Resolved | Target Release Date | Status | Resolution | Notes
1 | ALL | CEMO MoJ are receiving error messages when trying to send payloads | So far we are only looked at changes to historic orders that previously submitted correctly from prisons and probation. Bing has done an investigation and thinks it is the offence question: • We have changed what we send in this when it is empty which we thought fixed it but looks like that hasn't worked. • We have also tried trying to send it with an offence date and its still failing. |  | H | 2026-03-23 | 2026-03-25 |  | Closed | Fixed by MoJ CEMO team - now working | DFCT0011610
2 | CEMO610 | Single Offence sent | Committed Offences not updated on Mon Order |  | H | 2026-03-25 | 2026-04-20 |  | Ready for Prod | Single offence retested - now ok | DFCT0011622
3 | CEMO610 | Both IAS and TAS flags being sent | When requesting an IAS order, CEMO team has sent both IAS and TAS flags when only IAS is needed. CEMO team will fix it on their end |  | H | 2026-03-25 | 2026-04-02 |  | Closed | 01/04 - in progress. Lisa is hoping today 02/04 - retested and now ok | CEMO MoJ Team Issue
4 | CEMO610 | NO to responsible officer details received | CEMO team at the moment will always send No but this only applies to court orders. Prison orders will need yes. CEMO Team to fix |  | H | 2026-03-25 | 2026-04-07 |  | Closed | 01/04 - in review. should be able to test today 07/04 - retested and now ok | CEMO MoJ Team Issue
5 | CEMO608 | Unable to receive risk categories and details in CEMO | CEMO team unable to send risk categories and details. CEMO team to fix |  | H | 2026-03-25 | 2026-03-30 |  | Closed | Retested and now ok | CEMO MoJ Team Issue
6 |  | Order type for DAPO should be Pre Trial and not sending DAPO in Pilot | gone up to policy team as they were the ones who wanted Civil |  | H | 2026-03-25 | 2026-04-10 |  | Closed | 01/04 - blocked. Lisa is waiting on approval to send as Pretrial or Civil. She understands that the issue with Civil 02/04 - Lisa confirmed will be sending over as Pretrial and should be sending DAPO in pilot 07/04 - sending pre-trial but NO DAPO in pilot field 10/04 - DAPO in pilot field on CEMO MO form now being received | CEMO MoJ Team Issue
7 |  | Exclusion zone enforceable condition end date |  |  | H | 2026-03-25 | 2026-04-01 |  | Closed | 01/04 - not in this sprint but in the next one | CEMO MoJ Team Issue
8 | CEMO702 | MAPPA category is not reading in SNOW | CEMO selecting Mappa category, however system reads it as Mappa case type and hence SNOW is unable to add the category. CEMO team has found field |  | H | 30/03/2026 | 2026-04-08 |  | Closed | 01/04 - in progress. should be quick - 07/04 - MOJ team currently working on this, awaiting update 08/04 - restested and now receiving mappa category | CEMO MoJ Team Issue
9 | CEMO703 | Tag at Source not ticked for install at Immigration removal centre | Selecting "at another address" for install location does not tick the TAS checbox and no date/time for install is provided. This option is used for Install at Immigration removal centres and require a daytime appoitment. CEMO team to fix |  | H | 30/03/2026 | 2026-04-14 |  | Closed | 01/04 - bundled with IAS and TAS flags - 07/04 - MOJ fixed, retested and now okay | CEMO MoJ Team Issue
10 | All cases | EMS Case does not update to awaiting validation | fixed in previous phase - added step back in flow |  | H | 31/03/2026 | 2026-04-14 |  | Closed | 01/04 need to send emails to ML from preprod - requested - This is now corrected and working as expected | DFCT0011639
11 | All cases | EMS case receied with empty field under "Account" | For both New order and Variations received, Account is empty on the EMS page. Reason is, there is nothing filled in in the "no_name" field |  | H | 2026-04-02 | 2026-04-14 |  | Closed | MOJ has raised a bug ticket for it - 07/04 - MOJ team fixed it, retested and now its okay | CEMO MoJ Team Issue
12 | CEMOVAR11 CEMOVAR13 | Home Office Variations not restricted to CTC users | Order type = Immigration on both full and partial variation forms |  | H | 2026-04-02 | 2026-04-14 |  | Ready for Prod | 07/04 - Retested and now working as expected | DFCT0011644
13 |  | Mon Reqs and Mon Cons for HO are not being flagged as CTC anymore |  |  | H | 2026-04-08 | 2026-04-20 |  | Ready for Prod | DFCT655 cancelled and added to DFCT635 | DFCT0011655 DFCT0011635
14 | CEMO702 RETEST | MAPPA not captured correctly | MAPPA Level si reading in SNOW, MAPPA category is not reading in SNOW (screenshots in defects folder) |  | L | 2026-04-08 |  |  | Open | TRAINING: workaround will manually update MAPPA category | DFCT0011656
15 | ALL | PREPROD - CEMO PHASE 6 - Police Organisation | CEMO New Monitoring Order received with Greater Manchester Police Responsible Organisation however Mon was populated with Police |  | L | 2026-04-16 |  |  | Open | TRAINING: workaround will manually update mon order | DFCT0011678
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
6.1.25
Note on J1: Barlow, Beverley: Open - Draft, WIP Retest - BAT testing Ready for Prod - retest passed Training - workaround or info for training Closed - test data or raised in error On Hold - in future release