## Version Control
Document Information
Title | Test Execution Progress Log
Title | Feb Release - Bail ATV
Release Identifier | RLSE0010207 & RLSE0010208
Author | Beverley Barlow
Document Version History
Version | Date | Summary of Changes
0.1 | 18/01/2026 | Initial Definition of Test Cases
0.2 | 2026-01-31 | Final Copy for MOJ Review
Test Evidence Repository
Test Execution Evidence is stored at this link |  | Link to Test Evidence Repository
Scope of Release
This release implements a Servicenow upgrade
Defect/Story ID | Type | Details
STRY0087946 | Enhancement | Auto creation of enforcement cases on AL23 cases
STRY0087957 | Enhancement | Auto resolution of AL23 cases – non-immigration
STRY0087958 | Enhancement | Auto resolution of AL23 cases - Immigration
STRY0087959 | Enhancement | Auto set enforcement case fields when created from an AL23 case
STRY0087982 | Enhancement | Bulk update of AL23 cases to bring those in line with automation objective
STRY0088141 | Enhancement | AL08 & AL10 cases to auto resolve
STRY0088143 | Enhancement | KPI 6 Call made to not repopulate when second call is made

## Summary
|  |  | AL23 DASHBOARD |  |  |  | SHEET4 DASHBOARD |  |  |  | OVERALL DASHBOARD
Execution Progress |  |  |  | Execution Progress |  |  |  | Execution Progress
Steps Completed | 22 |  |  | Steps Completed | 0 |  |  | Steps Completed | 0
Steps Remaining | 0 |  |  | Steps Remaining | 0 |  |  | Steps Remaining | 0
Total Steps | 22 |  |  | Total Steps | 0 |  |  | Total Steps | 0
% Complete | 100% |  |  | % Complete | 0% |  |  | % Complete | #DIV/0!
Script Status |  |  |  | Script Status |  |  |  | Script Status
Pass | 6 | 100% |  | Pass | 0 | 0% |  | Pass | 0 | #DIV/0!
Fail | 0 | 0% |  | Fail | 0 | 0% |  | Fail | 0 | #DIV/0!
No Run | 0 | 0% |  | No Run | 0 | 0% |  | No Run | 0 | #DIV/0!
Not Completed | 0 | 0% |  | Not Completed | 0 | 0% |  | Not Completed | 0 | #DIV/0!
In Progress | 0 | 0% |  | In Progress | 0 | 0% |  | In Progress | 0 | #DIV/0!
Out of Scope | 0 | 0% |  | Out of Scope | 0 | 0% |  | Out of Scope | 0 | #DIV/0!
Not Started | 0 | 0% |  | Not Started | 0 | 0% |  | Not Started | 0 | #DIV/0!
TOTAL | 6 |  |  | TOTAL | 0 |  |  | TOTAL | 0
|  |  | ACQUISITIVE CRIME DASHBOARD |  |  | AL08 AL10 DASHBOARD
Execution Progress |  |  |  | Execution Progress
Steps Completed | 17 |  |  | Steps Completed | 66
Steps Remaining | 0 |  |  | Steps Remaining | 0
Total Steps | 17 |  |  | Total Steps | 66
% Complete | 100% |  |  | % Complete | 100%
Script Status |  |  |  | Script Status
Pass | 3 | 100% |  | Pass | 10 | 100%
Fail | 0 | 0% |  | Fail | 0 | 0%
No Run | 0 | 0% |  | No Run | 0 | 0%
Not Completed | 0 | 0% |  | Not Completed | 0 | 0%
In Progress | 0 | 0% |  | In Progress | 0 | 0%
Out of Scope | 0 | 0% |  | Out of Scope | 0 | 0%
Not Started | 0 | 0% |  | Not Started | 0 | 0%
TOTAL | 3 |  |  | TOTAL | 10

## AL23
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Data notes | Story
TT01 | Non Bail - Curfew - AL23 - call answered | - generate Charged Device Battery dead - PD call made - call answered - case left open - wait 15 mins from AL23 case creation | - AL23 created - API sent to PD - interaction created and closed - first response date updated for KPI6 - case auto closed after 15 mins with resolved state - enforcement AL105 case auto created with Category - Battery Breach, Sub-category - AL105 - Battery Breach, Reason for non-compliance - Battery Breach, Assignment group - Enforcement Team & first response date/time not updated | 5 | 5 | Pass |  | EMS13542862 retested - EMS13548940 | STRY0087957 STRY0087946 STRY0087959
TT02 | Bail - Curfew - AL23 - call not answered | - generate Charged Device Battery dead - PD call made - call not answered - case left open - wait 15 mins from AL23 case creation | - AL23 created - API sent to PD - no interaction created - first response date updated for KPI6 - AL09 attached to case - case auto closed after 15 mins with resolved state - enforcement AL105 case auto created with Category - Battery Breach, Sub-category - AL105 - Battery Breach, Reason for non-compliance - Battery Breach, Assignment group - Enforcement Team & first response date/time not updated | 5 | 5 | Pass |  | EMS13541753 | STRY0087957 STRY0087946 STRY0087959
TT03 | Bail - GPS - AL23 - call answered | - generate Charged Device Battery dead - PD call made - call answered - case left open - wait 15 mins from AL23 case creation | - AL23 created - API sent to PD - interaction created and closed - first response date updated for KPI6 - case auto closed after 15 mins with resolved state - enforcement AL105 case auto created with Category - Battery Breach, Sub-category - AL105 - Battery Breach, Reason for non-compliance - Battery Breach, Assignment group - Enforcement Team & first response date/time not updated | 5 | 5 | Pass |  | 28/01/2026 EMS13548950 | STRY0087957 STRY0087946 STRY0087959
TT04 | Non-Bail - GPS - AL23 - call not answered | - generate Charged Device Battery dead - PD call made - call not answered - case left open - wait 15 mins from AL23 case creation | - AL23 created - API sent to PD - no interaction created - first response date updated for KPI6 - AL09 attached to case - case auto closed after 15 mins with resolved state - enforcement AL105 case auto created with Category - Battery Breach, Sub-category - AL105 - Battery Breach, Reason for non-compliance - Battery Breach, Assignment group - Enforcement Agent & first response date/time not updated | 5 | 5 | Pass | user manually promoted to AL105 enforcement after 7 mins but AL23 was left in open state. system then auto generated AL105 after 15 mins & resolved case | EMS13549957 | STRY0087957 STRY0087946 STRY0087959
TT05 | Immigration - GPS - AL23 | - generate Charged Device Battery dead | - AL23 created - case auto closed with resolution code=completed & resolution notes: This Battery breach is related to an Immigration order and therefore no Enforcement case is required at this time. Should the Device wearer breach their ABV it will be managed under an AL15 case. | 1 | 1 | Pass |  | MON10119180 | STRY0087958
TT06 | Bulk update - New or Open AL23 (scripts cover immigration and non immigration | - run bulk script | - all historic active immigration AL23 records - resolved - all historic active non immigration AL23 cases with enforcement AL105 created - resolved - all historic active non immigration AL23 cases with PD outcome registered & no enforcement AL105 created - resolved & AL105 auto created | 1 | 1 | Pass | Run in preprod for all scripts covering New or Open AL23 (scripts cover immigration and non immigration |  | STRY0087982
Column1

## AL08_AL10
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Data notes | Story
ET01 | Non-Bail - Curfew only - AL08 | - generate Out Past Curfew - PD call made - call answered - case left open - generate Return home late after 15 mins - wait 6 hours from AL08 case creation | - AL08 generated - API sent to PD - interaction created and closed - first response date updated for KPI6 - AL09 attached to case - case auto closed after 6 hours & first response date/time not updated | 6 | 6 | Pass | create al08 before 9am 23/01/2026 | MON10119216 EMS13543913 | STRY0088141 STRY0088143
ET02 | Non Bail - Curfew - AL08 | - generate Out Past Curfew - PD call made - call not answered - case left open - generate Return home late investigation - wait 6 hours from AL08 case creation - create breach pack on AL13 | - AL08 generated - API sent to PD - no interaction created - first response date updated for KPI6 - AL09 attached to case - ATV AL13 generated - case auto closed after 6 hours & first response date/time not updated - breach pack created | 7 | 7 | Pass | retested as part of ET01 | EMS13541719 | STRY0088141 STRY0088143
ET03 | Non-Bail - Curfew only - AL10 | - generate Left home during Curfew 15 mins before end of curfew - PD call made - call not answered - case left open - generate Out at end of Curfew - wait 6 hours from AL10 case creation | - AL10 generated - API sent to PD - no interaction created - first response date updated for KPI6 - AL11 attached to case - case auto closed after 6 hours & first response date/time not updated | 6 | 6 | Pass | 6hrs is 22/01 @ 16:09 | EMS13542850, EMS13542817, EMS13542813 | STRY0088141 STRY0088143
ET04 | Non Bail - Curfew - AL10 | - generate Left home during Curfew - PD call made - call answered - case left open - generate Out at end of curfew investigation - wait 6 hours from AL10 case creation | - AL10 generated - API sent to PD - interaction created and closed - first response date updated for KPI6 - AL11 attached to case - case auto closed after 6 hours & first response date/time not updated | 6 | 6 | Pass |  | EMS13541707 | STRY0088141 STRY0088143
ET05 | Non-Bail - Curfew - AL08 | - generate Out Past Curfew - PD call made - call not answered - case left open - generate Return home late after 15 mins - wait 1 hour from AL08 case creation and resolve case manually - wait 6 hours from AL08 case creation | - AL08 generated - API sent to PD - interaction created and closed - first response date updated for KPI6 - AL09 attached to case - case resolved & first response date/time not updated - case still resolved after 6 hours (no update) | 7 | 7 | Pass |  | EMS13542852 set to resolved | STRY0088141 STRY0088143
ET06 | Non Bail - Curfew - AL10 | - generate Left home during Curfew 15 mins before end of curfew - PD call made - call not answered - case left open - generate Return home late - wait 1 hour from AL10 case creation and resolve case manually - wait 6 hours from AL10 case creation | - AL10 generated - API sent to PD - no interaction created - first response date updated for KPI6 - AL09 attached to case - case resolved & first response date/time not updated - case still resolved after 6 hours (no update) | 7 | 7 | Pass |  | EMS13542811 set to resolved | STRY0088141 STRY0088143
ET07 | Bail - Curfew - AL08 | - generate Out Past Curfew - PD call made - call answered - case left open - wait 15 mins for AL13 to generate - generate Return home late after AL13 (15 mins) generated - wait 6 hours from AL08 case creation - create breach pack | - AL08 generated - API sent to PD - interaction created and closed - first response date updated for KPI6 - AL09 attached to case - ATV AL13 generated - case auto closed after 6 hours & first response date/time not updated - breach pack created | 8 | 8 | Pass |  | EMS13540617 | STRY0088141 STRY0088143
ET08 | Bail - Curfew - AL08 | - generate Out Past Curfew - PD call made - call not answered - case left open - generate Return home late - wait 6 hours from AL08 case creation - create breach pack on AL13 | - AL08 generated - API sent to PD - no interaction created - first response date updated for KPI6 - AL09 attached to case - ATV AL13 generated - case auto closed after 6 hours & first response date/time not updated - breach pack created | 7 | 7 | Pass |  | EMS13540641 | STRY0088141 STRY0088143
ET09 | Bail - Curfew - AL10 | - generate Left home during Curfew 15 mins before end of curfew - PD call made - call not answered - case left open - generate Out at end of Curfew - wait 6 hours from AL10 case creation | - AL10 generated - API sent to PD - no interaction created - first response date updated for KPI6 - AL11 attached to case - ATV AL13 generated - case auto closed after 6 hours & first response date/time not updated | 6 | 6 | Pass |  | EMS13547895 | STRY0088141 STRY0088143
ET10 | Bail Curfew - AL10 | - generate Left home during Curfew - PD call made - call answered - case left open - generate Return home late after 10 mins - wait 6 hours from AL10 case creation | - AL10 generated - API sent to PD - interaction created and closed - first response date updated for KPI6 - AL09 attached to case - case auto closed after 6 hours & first response date/time not updated | 6 | 6 | Pass |  | EMS13540595 | STRY0088141 STRY0088143

## AcquisitiveCrime
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Test Data Used
AC01 | AC - AL08 | - generate Out Past Curfew - PD call made - call answered - case left open - generate Return home late after 15 mins - wait 6 hours from AL08 case creation | - AL08 generated - API sent to PD - interaction created and closed - first response date updated for KPI6 - AL09 attached to case - case auto closed after 6 hours & first response date/time not updated | 6 | 6 | Pass |  | MON10119242
AC02 | AC - AL10 | - generate Left home during Curfew 15 mins before end of curfew - PD call made - call not answered - case left open - generate Return home late - wait 6 hours from AL10 case creation | - AL10 generated - API sent to PD - no interaction created - first response date updated for KPI6 - AL09 attached to case - case auto closed after 6 hours & first response date/time not updated | 6 | 6 | Pass | EMS13541721 CREATED 21/01/2026 11:12
AC03 | AC - AL23 | - generate Charged Device Battery dead - PD call made - call answered - case left open - wait 15 mins from AL23 case creation | - AL23 created - API sent to PD - interaction created and closed - first response date updated for KPI6 - case auto closed after 15 mins with resolved state - enforcement AL105 case auto created with Category - Battery Breach, Sub-category - AL105 - Battery Breach, Reason for non-compliance - Battery Breach, Assignment group - Enforcement Team & first response date/time not updated | 5 | 5 | Pass |  | EMS13542871

## Sheet 4
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Test Data Used | Executed By | Approved By

## Validation (hidden)
Pass
Fail
No Run
Not Completed
In Progress
Out of Scope
Development
Blocked
Not Started

## Defects
Incident / JIRA ref | Test ID | Issue | Description | Category | Impact Rating (H-M-L) | Date Opened | Date Resolved | Target Release Date | Status | Post Production Check Y/N | Resolution | Release | Notes
1 | TT05 | Violation AL23 case is auto closing but First Call Outcome data field is empty | KPI6 report needs First Call Outcome date for calculation | KPI | H | 2026-01-19 | 2026-01-21 |  | Training | N | First Call Outcome data field is no accessible on Immigration records. Advised that Immigration orders are voided from KPI6 report and therefore First Call Outcome data not required |  | DFCT0011521
2 | TT04 | AL23 auto promotion to AL105 | User manually promoted AL23 to AL105 before the 15 mins - system still auto generated AL105 case after 15 mins - duplicate AL105 cases | KPI | H | 22/01/2026 | 23/01/2026 |  | Cancelled | N | Ops confirmed they would not be working within 15 min timescale - agreed to close defect |  | DFCT0011529
3 | TT01 | AL105 auto generated after 15 mins for an answered AL23 | Call for AL23 answered - AL23 case auto resolved around 1 min after AL23 case generated - AL105 did not generate until around 15 mins later | KPI | H | 22/01/2026 | 29/01/2026 |  | Ready for Prod | N | Retested now ok |  | DFCT0011530
4 | ET02 | work notes show 1970-01-01 this should be removed per UP3 |  | Work notes | H | 2026-01-22 | 2026-01-27 |  | Ready for Prod | N | Retested now ok
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
6.1.25
Note on J1: Barlow, Beverley (UK & Europe): Open, Fixed, Retest, Training, Closed

## Sheet1 (hidden)
Testing Timeline
| 19th |  | 20th |  | 21st | 24th | 25th | 26th | 27th | 28th
ST | OE44 * Install alcohol kit | ST | DV50 * Asset Manager BPSS persona | ST | 21st: DV50 * Asset Manager BPSS persona
KW | DV41 * Field Service Officer persona | ST | DV51 * Asset Manager CTC persona | ST | 21st: DV51 * Asset Manager CTC persona
KW | DV42 * Field Service Officer SPECIALS persona | ST | DV21 * Field Service Scheduler BPSS persona | ST | 21st: DV21 * Field Service Scheduler BPSS persona
LJ | DV44 * Quality Assurance CTC persona | ST | DV22 * Field Service Scheduler CTC persona | ST | 21st: DV22 * Field Service Scheduler CTC persona
EM | DV48 * CMT Immigration persona FAILED | TL / MHI | TA08 * atv breaches |  | 21st: TA31
EM | DV49 * CMT (MoJ) personas PASSED | ST | OEO7 * install following OE01 decom |  | 21st: TA10 / OE70
ST | OE69 * install NFD | EM | TA04 *EXCLUSION | EM | 21st: TA04 *EXCLUSION
EM | TA09 / OE69 * start the AL18 process | EM | TA30 *AL15 | EM | 21st: TA30 *AL15
TL / MHI | TA01 / OE01 * finish generating the atvs & breach packs | EM | TA47 * AL24 -SPOOF | EM | 21st: TA47 * AL24 -SPOOF
TL / MHI | TA52 / OE01 * generate AL04 | LJ | TA48 * AL20 |  | 21st: OE06
ST | TA43 / OE01 * request spoof event from AUEM | LJ | OE04 * check further visit has generated after previous visit booked off as faulty equipment |  | 21st: OE76
ST | OE01 * decom kit once event has been spoofed | ST | OE01 * decom kit |  | 21st: OE08
EM / ST & KW | OE04 * Create order * Assign WOT to Mark * 2x no show visits | ST | OE03 * 2x no show |  | 21st: TA41
ST & KW | OE03 * Assign WOT to Mark * 2x no show visits | TL / MHI | TA02 * 2x no show breach |  | 21st: OE09; 24th: NO SHOW
TL / MHI | TA05 / OE02 * Create multiple exclusions Day 1 | TL / MHI | TA05 / OE02 * Create multiple exclusions Day 2 |  | 21st: OE10; 24th: BOOK OFFS
TL / MHI & ST | TA11 / OE02 * Generate strap tamper * Complete tamper visit | TL / MHI | TA46 * breach |  | 21st: OE15
TL / MHI | TA33 / OE20 * battery dead | ST | TA03 * 2x no show |  | 21st: OE16
MS | OE08 * Create order | TL / MHI | TA03 * breach |  | 21st: OE17
MS | OE09 * Create order | ST | OE11 * 2x no show |  | 21st: OE12
MS | OE10 * Create order | TL / MHI | TA13 * breach |  | 21st: OE13
MS | OE11 * Create order | LJ | TA68 * breach | LJ | 21st: TA68 * breach
MS | OE12 * Create order | EM | OE18 * decom
MS | OE13 * Create order | MS | OE15 * create order
CL | OE45 * Create order | MS | OE16 * create order
CL | OE46 * Create order | MS | OE17 * create order
CL | OE47 * Create order | MS | OE19 * create order
ST | OE14 * decom kit | MS | OE21 * create order
ST | OE20 * install kit | MS | OE22 * create order
TL / MHI | TA08 * start atv breaches | MS | OE23 * create order
|  | MS | OE24 * create order
|  | MS | OE25 * create order
|  | MS | OE26 * create order | MS | 21st: OE26 * create order
|  | MS | OE27 * create order
|  | MS | OE28 * create order | MS | 21st: OE28 * create order
|  | CL | OE29 * create order | MS | 21st: OE29 * create order
|  | CL | OE30 * create order | MS | 21st: OE30 * create order
|  | CL | OE31 * create order | MS | 21st: OE31 * create order
|  | CL | AC01 * create order | CL | 21st: AC01 * create order
|  | CL | AC02 * create order | CL | 21st: AC02 * create order
|  | CL | AC03 * create order | CL | 21st: AC03 * create order
|  | CL | AC04 * create order | CL | 21st: AC04 * create order
|  | LJ | DV41 * Field Service Officer persona
|  | LJ | DV42 * Field Service Officer SPECIALS persona
|  | LJ | TA40 * once the 2x no shows are complete - create a new installation work order
|  | ST | TA40 * threatening words & behaviour
|  | LJ | TA40 * breach
|  | TL / MHI | TA58 * aggregation
|  | TL / MHI | TA59 * aggregation
|  | TL / MHI | TA60 * aggregation |  | 21st: TA60 * aggregation
|  | TL / MHI | TA61 * aggregation |  | 21st: TA61 * aggregation
|  | TL / MHI | TA62 * aggregation |  | 21st: TA62 * aggregation
|  | ST | TA46 * 1x threatening words & behaviour
|  | EM | TA46 * breach
|  | LJ | OE49
|  | LJ | OE50

## OVERALL
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Issue/Defect | SERCO JIRA ID | SNOW defect ID | Approved By
0