## Version Control
Document Information
Title | Test Execution Progress Log
Title | Feb Release - Bail ATV
Release Identifier | RLSE0010196
Author | Beverley Barlow
Document Version History
Version | Date | Summary of Changes
0.1 | 2026-01-05 | Initial Definition of Test Cases
0.2 | 2026-01-31 | Final Copy for MOJ Review
Test Evidence Repository
Test Execution Evidence is stored at this link |  | Link to Test Evidence Repository
Scope of Release
This release implements a Servicenow upgrade
Defect/Story ID | Type | Details
STRY0084697 | Enhancement | Bail S9 ATV statement when no end event is present
STRY0084698 | Enhancement | Bail S9 ATV statement when end event IS present
STRY0085026 | Enhancement | Bail S9 ATV statement when Out for entire curfew period
STRY0085027 | Enhancement | New field to capture pre-trial threshold met time
STRY0085703 | Enhancement | DAPO S9 ATV statement when end event IS present
STRY0085710 | Enhancement | DAPO S9 ATV statement when no end event present
STRY0085711 | Enhancement | DAPO S9 ATV statement when Out for entire curfew period
STRY0085718 | Enhancement | Ensure Bail S9 packs are generated for MO's under RF/GPS extradition descriptions
STRY0085755 | Enhancement | ATV wording for Immigration bail breach packs

## Summary
|  |  | ORDERS DASHBOARD |  |  |  | SHEET4 DASHBOARD |  |  |  | OVERALL DASHBOARD
Execution Progress |  |  |  | Execution Progress |  |  |  | Execution Progress
Steps Completed | 137 |  |  | Steps Completed | 0 |  |  | Steps Completed | 0
Steps Remaining | 0 |  |  | Steps Remaining | 0 |  |  | Steps Remaining | 0
Total Steps | 137 |  |  | Total Steps | 0 |  |  | Total Steps | 0
% Complete | 100% |  |  | % Complete | #DIV/0! |  |  | % Complete | #DIV/0!
Script Status |  |  |  | Script Status |  |  |  | Script Status
Pass | 14 | 100% |  | Pass | 0 | #DIV/0! |  | Pass | 0 | #DIV/0!
Fail | 0 | 0% |  | Fail | 0 | #DIV/0! |  | Fail | 0 | #DIV/0!
No Run | 0 | 0% |  | No Run | 0 | #DIV/0! |  | No Run | 0 | #DIV/0!
Not Completed | 0 | 0% |  | Not Completed | 0 | #DIV/0! |  | Not Completed | 0 | #DIV/0!
In Progress | 0 | 0% |  | In Progress | 0 | #DIV/0! |  | In Progress | 0 | #DIV/0!
Out of Scope | 0 | 0% |  | Out of Scope | 0 | #DIV/0! |  | Out of Scope | 0 | #DIV/0!
Not Started | 0 | 0% |  | Not Started | 0 | #DIV/0! |  | Not Started | 0 | #DIV/0!
TOTAL | 14 |  |  | TOTAL | 0 |  |  | TOTAL | 0
|  |  | ACQUISITIVE CRIME DASHBOARD |  |  | BAIL ATV DASHBOARD
Execution Progress |  |  |  | Execution Progress
Steps Completed | 14 |  |  | Steps Completed | 101
Steps Remaining | 0 |  |  | Steps Remaining | 0
Total Steps | 14 |  |  | Total Steps | 101
% Complete | 100% |  |  | % Complete | 100%
Script Status |  |  |  | Script Status
Pass | 3 | 100% |  | Pass | 35 | 76.09%
Fail | 0 | 0% |  | Fail | 0 | 0%
No Run | 0 | 0% |  | No Run | 0 | 0%
Not Completed | 0 | 0% |  | Not Completed | 0 | 0%
In Progress | 0 | 0% |  | In Progress | 0 | 0%
Out of Scope | 0 | 0% |  | Out of Scope | 11 | 23.91%
Not Started | 0 | 0% |  | Not Started | 0 | 0%
TOTAL | 3 |  |  | TOTAL | 46

## ORDERS
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Test Data Used | Tests
BC01 | Adult - New Order - Verified Address - RF Bail-Curfew only | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass | defects on the interaction DFCT0011478 - defect did not halt the order creation | DEVWR0101629 / MON10119176 | BA01 BA02 BA03 BA04 BA21 BA33
BC02 | Adult-Non-Bail-Community-curfew | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass | defects on the interaction DFCT0011478 - defect did not halt the order creation | DEVWR0101633 / MON10119178 | BA05 BA06 BA07 BA08 BA22 BA34
BC03 | Immigration-GPS | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass |  | DEVWR0101642 / MON10119180 | BA09 BA10 BA11 BA12 BA23 BA37
BC04 | DAPO | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass |  | DEVWR0101648 / MON10119183 | BA13 BA14 BA15 BA16 BA24
BC05 | Bail-RF Extradition | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass |  | DEVWR0101650 / MON10119184 | BA17 BA18
BC06 | Bail-GPS-Extradition | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass |  | DEVWR0101655 / MON10119189 | BA19 BA20
BC07 | Adult-Bail-Curfew and exculsion | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass |  | DEVWR0101657 / MON10119190 | BA25 BA27
BC08 | Adult-Non-Bail-Curfew and exculsion | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass |  | DEVWR0101659 / MON10119191 | BA26 BA28
BC09 | Adult - New Order - Verified Address - RF Bail-Curfew only | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task | - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass |  | MON10119194/ DEVWR0101662 | BA29 BA31
BC10 | Adult-Non-Bail-Community-curfew | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task | - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass |  | DEVWR0101665/ MON10119196 | BA30 BA32
BC11 | Immigration-GPS | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task | - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass |  | DEVWR0101667/ MON10119197 | BA35 BA36
BC12 | Child - New Order - Verified Address - RF Bail-Curfew only | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass |  | DEVWR0101671/ MON10119199 | BA38 BA39 BA40 BA41
BC13 | Child-Non-Bail-Post Release - HDC (SECTON 91) | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass |  | DEVWR0101644/ MON10119181 | BA42 BA43 BA44 BA45
BC14 | Immigration-NFD | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass |  | DEVWR0101774 / MON10119302 | BA46
Column1

## Bail ATV
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Data notes
BA01 | Bail - GPS - ATV | 15 min in 1 event for same curfew period - create breach pack | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass |  | BC01
BA02 | Bail - GPS - ATV | 15 min over 2 or 3 events for same curfew period - create breach pack | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass | For example: DW curfew 10am - 2pm Violation 1 - 10.10.00 - 10.15.30 Duration = 5 mins 30 seconds Violation 2 - 10.30.00 - 10.38.15 Duration = 8 mins 15 seconds Violation 3 - 11.02.00 - DW still out when 15 mins reached Remaining time left from the 15 min duration: 15 min - 5 min 30 seconds - 8 mins 15 seconds = 1 minute 15 seconds ATV threshold met = 11.02.00 + 1 min 15 seconds = 05/12/2025 11:03:15 | BC01
BA03 | Bail - GPS - ATV | 15 min over 2 or 3 events - over 2 curfew periods | AL08/AL10 case generated | 1 | 1 | Pass |  | BC01
BA04 | Bail - GPS - ATV | 15 min in 1 event for same curfew period - create breach pack before return | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass |  | BC01
BA05 | Non-Bail - GPS - ATV | 2 hours in 1 event for same curfew period | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass |  | BC02
BA06 | Non-Bail - GPS - ATV | 2 hours over 2 or 3 events for same curfew period | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass | "For example: DW curfew 10am - 2pm Violation 1 - 10.10.00 - 11.15.30 Duration = 1 hour 5 mins 30 seconds Violation 2 - 11:30:00 - 11:58:15 Duration = 28 mins 15 seconds Violation 3 - 12.02.00 - DW still out when 2 hours reached Remaining time left from the 2 hours duration: 15 min - 1 hour 5 min 30 seconds - 28 mins 15 seconds = 26 minute 15 seconds ATV threshold met = 12.02.00 + 26 min 15 seconds = 05/12/2025 12:28:15" | BC02
BA07 | Non-Bail - GPS - ATV | 2 hours over 2 or 3 events - over 2 curfew periods | AL08/AL10 case generated | 1 | 1 | Pass |  | BC02
BA08 | Non-Bail - GPS - ATV | 2 Hours in 1 event for same curfew period - create breach pack before return | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Out of Scope | Non-bail aggregates time breaches based on start/end periods on AL08 and AL10 - this is not a valid test | BC02
BA09 | Immigration-GPS-ATV | 2 hours in 1 event for same curfew period | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Out of Scope | 'Currently not getting curfew orders | BC03
BA10 | Immigration-GPS-ATV | 2 hours over 2 or 3 events for same curfew period | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Out of Scope | 'Currently not getting curfew orders | BC03
BA11 | Immigration-GPS-ATV | 2 hours over 2 or 3 events - over 2 curfew periods | AL08/AL10 case generated | 1 | 1 | Out of Scope | 'Currently not getting curfew orders | BC03
BA12 | Immigration-GPS-ATV | 2 Hours in 1 event for same curfew period - create breach pack before return | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Out of Scope | 'Currently not getting curfew orders | BC03
BA13 | DAPO - RF - ATV | 15 min in 1 event for same curfew period - create breach pack | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass | Passed evidence attached | BC04
BA14 | DAPO - RF - ATV | 15 min over 2 or 3 events for same curfew period - create breach pack 15 min over 2 events in same curfew - device not returned create breach pack | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass | For example: DW curfew 10am - 2pm Violation 1 - 10.10.00 - 10.15.30 Duration = 5 mins 30 seconds Violation 2 - 10.30.00 - 10.38.15 Duration = 8 mins 15 seconds Violation 3 - 11.02.00 - DW still out when 15 mins reached Remaining time left from the 15 min duration: 15 min - 5 min 30 seconds - 8 mins 15 seconds = 1 minute 15 seconds ATV threshold met = 11.02.00 + 1 min 15 seconds = 05/12/2025 11:03:15 | BC04
BA15 | DAPO - RF - ATV | 15 min over 2 or 3 events - over 2 curfew periods | AL08/AL10 case generated | 1 | 1 | Pass |  | BC04
BA16 | DAPO - RF - ATV | 15 min in 1 event for same curfew period - create breach pack before return | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass |  | BC04
BA17 | Bail-RF Extradition | 15 min in 1 event for same curfew period - create breach pack | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass |  | BC05
BA18 | Bail-RF Extradition | 15 min over 2 or 3 events for same curfew period - create breach pack | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass | "For example: DW curfew 10am - 2pm Violation 1 - 10.10.00 - 10.15.30 Duration = 5 mins 30 seconds Violation 2 - 10.30.00 - 10.38.15 Duration = 8 mins 15 seconds Violation 3 - 11.02.00 - DW still out when 15 mins reached Remaining time left from the 15 min duration: 15 min - 5 min 30 seconds - 8 mins 15 seconds = 1 minute 15 seconds ATV threshold met = 11.02.00 + 1 min 15 seconds = 05/12/2025 11:03:15" | BC05
BA19 | Bail-GPS Extradition | 15 min in 1 event for same curfew period - create breach pack | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass |  | BC06
BA20 | Bail-GPS Extradition | 15 min over 2 or 3 events for same curfew period - create breach pack | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass | "For example: DW curfew 10am - 2pm Violation 1 - 10.10.00 - 10.15.30 Duration = 5 mins 30 seconds Violation 2 - 10.30.00 - 10.38.15 Duration = 8 mins 15 seconds Violation 3 - 11.02.00 - DW still out when 15 mins reached Remaining time left from the 15 min duration: 15 min - 5 min 30 seconds - 8 mins 15 seconds = 1 minute 15 seconds ATV threshold met = 11.02.00 + 1 min 15 seconds = 05/12/2025 11:03:15" | BC06
BA21 | Bail - RF - ATV | Out for whole curfew | AL08 to generated followed by AL12 | 1 | 1 | Out of Scope | No event for whole curfew - triggered from full period of breach. As breach occurs after 15 mins regardless of whether end event received - not applicable | BC01
BA22 | Non-Bail - GPS - ATV | Out for whole curfew | AL08 to generated followed by AL12 | 1 | 1 | Pass |  | BC02
BA23 | Immigration-GPS-ATV | Out for whole curfew | AL08 to generated followed by AL12 | 1 | 1 | Out of Scope | 'Currently not getting curfew orders | BC03
BA24 | DAPO - RF - ATV | Out for whole curfew | AL08 to generated followed by AL12 | 1 | 1 | Out of Scope | No event for whole curfew - triggered from full period of breach. As breach occurs after 15 mins regardless of whether end event received - not applicable | BC04
BA25 | Bail-GPS-Curfew & Exclusion | Create exclusion breach AL06 Generated breach pack generated after 7 am | 1 case generated 7am - 6.59am | 3 | 3 | Pass |  | BC07
BA26 | Non-Bail - GPS-Curfew & Exclusion | Create exclusion breach AL06 Generated breach pack generated after 7 am | 1 case generated 7am - 6.59am | 3 | 3 | Pass |  | MON10119168
BA27 | Bail - RF - ATV | - create strap tamper AL03 Will Generate - create visit to confirm Tamper visited booked off as confirmed tamper manully protmote to AL104 | - AL03 case generated - AL104 manually Generated after visit | 5 | 5 | Pass |  | BC07
BA28 | Non-Bail - GPS-Curfew & Exclusion | "- create strap tamper AL03 Will Generate - create visit to confirm Tamper visited booked off as confirmed tamper manully protmote to AL104" | - AL03 case generated - AL104 manually Generated after visit | 5 | 5 | Out of Scope | duplicate of BA26 | BC08
BA29 | Bail - RF - ATV | 1. Task install visit - book off as no show 2. Task 2nd attempt visit - book off as no show 3. Create breach pack | AL100 generated | 3 | 3 | Pass | 2x no show done | BC09
BA30 | Non-Bail - GPS - ATV | 1. Task install visit - book off as no show 2. Task 2nd attempt visit - book off as no show 3. Create breach pack | AL100 to be generated | 3 | 3 | Pass | 2x no show done | BC10
BA31 | Bail - RF - ATV | 1. Task install visit - book off as WOC 2. Create breach pack | AL102 generated | 2 | 2 | Pass |  | BC09
BA32 | Non-Bail - GPS - ATV | 1. Task install visit - book off as WOC 2. Create breach pack | AL102 generated | 2 | 2 | Pass |  | BC10
BA33 | Bail - RF - ATV | 1. Generate tamper 2.AL03-Generated, create visit to comfirm Tamper 3. Book off as confirmed tamper 4. Create breach | AL104 manually Generated after visit | 4 | 4 | Out of Scope | duplicate of BA27 | BC01
BA34 | Non-Bail - GPS - ATV | 1. Generate tamper 2.AL03-Generated, create visit to comfirm Tamper 3. Book off as confirmed tamper 4. Create breach | AL104 manually Generated after visit | 4 | 4 | Pass |  | BC02
BA35 | Immigration-GPS-ATV | 1. Task install visit - book off as no show 2. Task 2nd attempt visit - book off as no show 3. Create breach pack | AL100 generated | 3 | 3 | Pass | 2x no show done | BC11
BA36 | Immigration-GPS-WOC | 1. Task install visit - book off as WOC 2. Create breach pack | AL102 generated | 2 | 2 | Pass | QK AND KL from Immigration signed off on breach pack | BC11
BA37 | Immigration-GPS-ATV (TAMPER & EXCLUSION) | 1. Generate tamper 2.AL02-Generated 3. Create visit to comfirm Tamper 4. Book off as confirmed tamper 5. Create breach | AL104 manually Generated after visit | 5 | 5 | Pass | confirmed with Immigration team | BC03
BA38 | Bail - RF - ATV-Child | 15 min in 1 event for same curfew period - create breach pack | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass |  | BC12
BA39 | Bail - RF - ATV-Child | 15 min over 2 or 3 events for same curfew period - create breach pack | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass | For example: DW curfew 10am - 2pm Violation 1 - 10.10.00 - 10.15.30 Duration = 5 mins 30 seconds Violation 2 - 10.30.00 - 10.38.15 Duration = 8 mins 15 seconds Violation 3 - 11.02.00 - DW still out when 15 mins reached Remaining time left from the 15 min duration: 15 min - 5 min 30 seconds - 8 mins 15 seconds = 1 minute 15 seconds ATV threshold met = 11.02.00 + 1 min 15 seconds = 05/12/2025 11:03:15 | BC12
BA40 | Bail - RF - ATV-Child | 15 min over 2 or 3 events - over 2 curfew periods | AL08/AL10 case generated | 1 | 1 | Pass |  | BC12
BA41 | Bail - RF - ATV-Child | 15 min in 1 event for same curfew period - create breach pack before return | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass |  | BC12
BA42 | Child-Non-Bail-Post Release - HDC (SECTON 91) | 2 hours in 1 event for same curfew period | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass |  | BC13
BA43 | Child-Non-Bail-Post Release - HDC (SECTON 91) | 2 hours over 2 or 3 events for same curfew period | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Pass | For example: DW curfew 8am - 10.30am Violation 1 - 08.00 - 09.00 ACTUAL 08:02:18 -09:11:29 Duration = 1 hour ACTUAL 1hr 9m 11s Violation 2 - 09.10 - 10.00 ACTUAL 09:24:53 -09:58:57 Duration = 50 min ACTUAL 34 m 4s Violation 3 - 10.15 - DW still out when 2 hours reached ACTUAL 10:03:29 - 10:30 Remaining time left from the 2hours duration: 10 min ACTUAL 26m 21s ATV threshold met = 10.25 (2hr 9 36 sec) ACTUAL10.20.14 | BC13
BA44 | Child-Non-Bail-Post Release - HDC (SECTON 91) | 2 hours over 2 or 3 events - over 2 curfew periods | AL08/AL10 case generated | 2 | 2 | Pass | DW curfew 09:00- 11:30, 12:00-14:30 ACTUAL 09:13:55-10:14:08-1 HOUR 13 SECONDS Actual 09:00:00-10:03:31 | BC13
BA45 | Child-Non-Bail-Post Release - HDC (SECTON 91) | 2 Hours in 1 event for same curfew period - create breach pack before return | AL08/AL10 case generated followed by AL13 case generated | 2 | 2 | Out of Scope | Non-bail aggregates time breaches based on start/end periods on AL08 and AL10 - this is not a valid test | BC13
BA46 | NFD Order creation and missed biometric | Miss x 3 biometrics This should then create a AL18 |  | 2 | 2 | Pass |  | BC14

## AcquisitiveCrime
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Test Data Used
BB01 | Adult/New Order/Verified address/GPS Acquisitive Crime Parole/Curfew & Exclsuion | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. create Work Order Task 10. install solo and hmu | - interaction, case, mon order, work order and work order task created - devices installed, mon order live | 10 | 10 | Pass |  | MON10119242 / DEVWR0101728
BB02 | AC-ATV | 2 hours in 1 event for same curfew period al08 will generate al13 will generate create enforcement action | AL08/AL10 case generated followed by AL13 case generated | 1 | 1 | Pass |  | Follow on from BB01
BB03 | AC-GPS-EXCLSUION | Create exclusion breach AL06 Generated breach pack generated create enforcement action | 1 case generated 7am - 6.59am | 3 | 3 | Pass |  | Follow on from BB02

## Sheet 4
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Test Data Used | Executed By | Approved By

## Validation (hidden)
Pass
Fail
No Run
Not Completed
In Progress
Out of Scope
Development
Blocked
Not Started

## Defects
Incident / JIRA ref | Test ID | Issue | Description | Category | Impact Rating (H-M-L) | Date Opened | Date Resolved | Target Release Date | Status | Post Production Check Y/N | Resolution | Release | Notes
1 |  | create a decom - no names displaying on a case |  |  |  | 2026-01-19 | 19/01/2026 |  | Closed Complete | N | test data issue |  | DFCT0011517
2 | BA14 | Exhibit 06 being in the Breach document when it shouldn’t be there | PE/06 only seems to be appearing for DAPO notifications - PE/06 does not appear in standard bail notifications |  |  | 19/01/2026 | 23/01/2026 |  | Ready for Prod | N | retested |  | DFCT0011522
3 | BA14 | 15 minute threshold not showing correct time and instead showing Not available | 15 minute threshold not calculating for multiple atvs - seems to be occurring on DAPO only |  |  | 19/01/2026 | 2026-01-31 |  | Ready for Prod | N | retested |  | DFCT0011523
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
6.1.25
Note on J1: Barlow, Beverley (UK & Europe): Open, Fixed, Retest, Training, Closed

## Sheet1 (hidden)
Testing Timeline
| 19th |  | 20th |  | 21st | 24th | 25th | 26th | 27th | 28th
ST | OE44 * Install alcohol kit | ST | DV50 * Asset Manager BPSS persona | ST | DV50 * Asset Manager BPSS persona
KW | DV41 * Field Service Officer persona | ST | DV51 * Asset Manager CTC persona | ST | DV51 * Asset Manager CTC persona
KW | DV42 * Field Service Officer SPECIALS persona | ST | DV21 * Field Service Scheduler BPSS persona | ST | DV21 * Field Service Scheduler BPSS persona
LJ | DV44 * Quality Assurance CTC persona | ST | DV22 * Field Service Scheduler CTC persona | ST | DV22 * Field Service Scheduler CTC persona
EM | DV48 * CMT Immigration persona FAILED | TL / MHI | TA08 * atv breaches |  | TA31
EM | DV49 * CMT (MoJ) personas PASSED | ST | OEO7 * install following OE01 decom |  | TA10 / OE70
ST | OE69 * install NFD | EM | TA04 *EXCLUSION | EM | TA04 *EXCLUSION
EM | TA09 / OE69 * start the AL18 process | EM | TA30 *AL15 | EM | TA30 *AL15
TL / MHI | TA01 / OE01 * finish generating the atvs & breach packs | EM | TA47 * AL24 -SPOOF | EM | TA47 * AL24 -SPOOF
TL / MHI | TA52 / OE01 * generate AL04 | LJ | TA48 * AL20 |  | OE06
ST | TA43 / OE01 * request spoof event from AUEM | LJ | OE04 * check further visit has generated after previous visit booked off as faulty equipment |  | OE76
ST | OE01 * decom kit once event has been spoofed | ST | OE01 * decom kit |  | OE08
EM / ST & KW | OE04 * Create order * Assign WOT to Mark * 2x no show visits | ST | OE03 * 2x no show |  | TA41
ST & KW | OE03 * Assign WOT to Mark * 2x no show visits | TL / MHI | TA02 * 2x no show breach |  | OE09 | NO SHOW
TL / MHI | TA05 / OE02 * Create multiple exclusions Day 1 | TL / MHI | TA05 / OE02 * Create multiple exclusions Day 2 |  | OE10 | BOOK OFFS
TL / MHI & ST | TA11 / OE02 * Generate strap tamper * Complete tamper visit | TL / MHI | TA46 * breach |  | OE15
TL / MHI | TA33 / OE20 * battery dead | ST | TA03 * 2x no show |  | OE16
MS | OE08 * Create order | TL / MHI | TA03 * breach |  | OE17
MS | OE09 * Create order | ST | OE11 * 2x no show |  | OE12
MS | OE10 * Create order | TL / MHI | TA13 * breach |  | OE13
MS | OE11 * Create order | LJ | TA68 * breach | LJ | TA68 * breach
MS | OE12 * Create order | EM | OE18 * decom
MS | OE13 * Create order | MS | OE15 * create order
CL | OE45 * Create order | MS | OE16 * create order
CL | OE46 * Create order | MS | OE17 * create order
CL | OE47 * Create order | MS | OE19 * create order
ST | OE14 * decom kit | MS | OE21 * create order
ST | OE20 * install kit | MS | OE22 * create order
TL / MHI | TA08 * start atv breaches | MS | OE23 * create order
|  | MS | OE24 * create order
|  | MS | OE25 * create order
|  | MS | OE26 * create order | MS | OE26 * create order
|  | MS | OE27 * create order
|  | MS | OE28 * create order | MS | OE28 * create order
|  | CL | OE29 * create order | MS | OE29 * create order
|  | CL | OE30 * create order | MS | OE30 * create order
|  | CL | OE31 * create order | MS | OE31 * create order
|  | CL | AC01 * create order | CL | AC01 * create order
|  | CL | AC02 * create order | CL | AC02 * create order
|  | CL | AC03 * create order | CL | AC03 * create order
|  | CL | AC04 * create order | CL | AC04 * create order
|  | LJ | DV41 * Field Service Officer persona
|  | LJ | DV42 * Field Service Officer SPECIALS persona
|  | LJ | TA40 * once the 2x no shows are complete - create a new installation work order
|  | ST | TA40 * threatening words & behaviour
|  | LJ | TA40 * breach
|  | TL / MHI | TA58 * aggregation
|  | TL / MHI | TA59 * aggregation
|  | TL / MHI | TA60 * aggregation |  | TA60 * aggregation
|  | TL / MHI | TA61 * aggregation |  | TA61 * aggregation
|  | TL / MHI | TA62 * aggregation |  | TA62 * aggregation
|  | ST | TA46 * 1x threatening words & behaviour
|  | EM | TA46 * breach
|  | LJ | OE49
|  | LJ | OE50

## OVERALL
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Issue/Defect | SERCO JIRA ID | SNOW defect ID | Approved By
0