## Version Control
Document Information
Title | Test Execution Progress Log
Title | Feb Release - CEMO Phase 5
Release Identifier | RLSE0010167
Author | Beverley Barlow
Document Version History
Version | Date | Summary of Changes
0.1 | 2026-05-01 | Initial Definition of Test Cases
0.2 | 2026-01-30 | Final Issue for MOJ Review
Test Evidence Repository
Test Execution Evidence is stored at this link |  | Link to Test Evidence Repository
Scope of Release
This release implements a Servicenow upgrade
Defect/Story ID | Type | Details
STRY0082724 | Enhancement | CEMO - Update to the CEMO variation Process
STRY0082729 | Enhancement | CEMO Temporary Variation solution
STRY0084042 | Enhancement | Logic moved out of Scripted REST API filles into re-usable script includes.
STRY0084043 | Enhancement | Create a functional CEMO Script Include
STRY0084048 | Enhancement | Create a CEMO Constants Script Include
STRY0084116 | Enhancement | [CEMO] Install at Source pilot field on the CEMO MO
STRY0084134 | Enhancement | [CEMO] DAPOL field to only appear where a DAPOL order is selected
STRY0085010 | Enhancement | Up the character limit on 2 CEMO fields
STRY0086235 | Enhancement | CEMO Monitoring Order schema update

## Summary
|  |  | ACQUISITIVE CRIME DASHBOARD |  |  |  | SHEET4 DASHBOARD |  |  |  | OVERALL DASHBOARD
Execution Progress |  |  |  | Execution Progress |  |  |  | Execution Progress
Steps Completed | 29 |  |  | Steps Completed | 0 |  |  | Steps Completed | 0
Steps Remaining | 0 |  |  | Steps Remaining | 0 |  |  | Steps Remaining | 0
Total Steps | 29 |  |  | Total Steps | 0 |  |  | Total Steps | 0
% Complete | 100% |  |  | % Complete | #DIV/0! |  |  | % Complete | #DIV/0!
Script Status |  |  |  | Script Status |  |  |  | Script Status
Pass | 3 | 100% |  | Pass | 0 | #DIV/0! |  | Pass | 0 | #DIV/0!
Fail | 0 | 0% |  | Fail | 0 | #DIV/0! |  | Fail | 0 | #DIV/0!
No Run | 0 | 0% |  | No Run | 0 | #DIV/0! |  | No Run | 0 | #DIV/0!
Not Completed | 0 | 0% |  | Not Completed | 0 | #DIV/0! |  | Not Completed | 0 | #DIV/0!
In Progress | 0 | 0% |  | In Progress | 0 | #DIV/0! |  | In Progress | 0 | #DIV/0!
Out of Scope | 0 | 0% |  | Out of Scope | 0 | #DIV/0! |  | Out of Scope | 0 | #DIV/0!
Not Started | 0 | 0% |  | Not Started | 0 | #DIV/0! |  | Not Started | 0 | #DIV/0!
TOTAL | 3 |  |  | TOTAL | 0 |  |  | TOTAL | 0
|  |  | VARIATIONS DASHBOARD |  |  | PHASE5 DASHBOARD
Execution Progress |  |  |  | Execution Progress
Steps Completed | 102 |  |  | Steps Completed | 208
Steps Remaining | 0 |  |  | Steps Remaining | 0
Total Steps | 102 |  |  | Total Steps | 208
% Complete | 100% |  |  | % Complete | 100%
Script Status |  |  |  | Script Status
Pass | 14 | 93.33% |  | Pass | 23 | 100%
Fail | 0 | 0% |  | Fail | 0 | 0%
No Run | 0 | 0% |  | No Run | 0 | 0%
Not Completed | 0 | 0% |  | Not Completed | 0 | 0%
In Progress | 0 | 0% |  | In Progress | 0 | 0%
Out of Scope | 1 | 6.667% |  | Out of Scope | 0 | 0%
Not Started | 0 | 0% |  | Not Started | 0 | 0%
TOTAL | 15 |  |  | TOTAL | 23

## Phase 5
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Data notes | Tested by
CEMO01 | CEMO/Adult/New Order/Verified address/GPS Dapol GPS Parole/RF & Exclusion/Inclusion | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass | 3 addresses MON10119165 |  | Calvin
CEMO02 | CEMO/Adult/New Order/Verified address/GPS Dapol GPS Parole/RF & Trail | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass | MON10119219 |  | Calvin
CEMO03 | CEMO/Adult/New Order/Verified address/GPS Dapol GPS Parole/Exclusion/Inclusion | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass | MON10119220 |  | Calvin
CEMO04 | CEMO/Adult/New Order/Verified address/GPS Dapol GPS Parole/Trail | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass | MON10119222
CEMO05 | CEMO/Adult/New Order/Verified address/GPS Dapol GPS Parole/Trail & Exclusion/Inclusion | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass | MON10119223 |  | Calvin
CEMO06 | CEMO/Adult/New Order/Verified address/HDC/RF | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10. Install | - cemo new order API received - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass | WOT0431069 MON10119175 SR04 - AV | today | Calvin
CEMO07 | CEMO/Adult/New Order/Verified address/HDC with AM/Alcohol Monitoring AML & RF | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created - devices installed, mon order live | 9 | 9 | Pass | MON10119227 (non am) MON10119235 (am) |  | Calvin
CEMO08 | CEMO/Adult/New Order/Verified address/HDC with AM/Alcohol Monitoring AML, RF, Trail & Exclusion/Inclusion | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass | MON10119239 (AM) / MON10119237 (non-am) |  | Calvin
CEMO09 | CEMO/Adult/New Order/Verified address/Parole Licence with AM/Alcohol Monitoring AML | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass | MON10119229 |  | Calvin
CEMO10 | CEMO/Adult/New Order/NFA/Release on Licence with AM/Alcohol Monitoring AML | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass
CEMO11 | CEMO/Child/New Order/Verified address/DTO YOT/RF | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass |  |  | Kayode
CEMO12 | CEMO/Child/New Order/Verified address/GPS DTO YOT/RF & Exclusion/Inclusion | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created - devices installed, mon order live | 9 | 9 | Pass |  |  | Kayode
CEMO13 | CEMO/Child/New Order/Verified address/GPS DTO YOT/RF & Trail | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass |  |  | Kayode
CEMO14 | CEMO/Child/New Order/Verified address/HDC (Section 91)/RF & Inclusion/Exclusion | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass | Disabilities failed to pull through to the DW profile. Now fixed | DEVWR0101744, MON10119254 | Kayode
CEMO15 | CEMO/Child/New Order/Verified address/HDC (Section 91)/RF & Trail | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass |  |  | Kayode
CEMO16 | CEMO/Child/New Order/Verified address/HDC (Section 91)/RF, Exclusion/Inclusion & Trail | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass |  |  | Calvin
CEMO17 | CEMO/Child/New Order/Verified address/HDC (Section 91)/RF | 1. create Interaction 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass | MON10119167 - WOT0431028 |  | Calvin
CEMO18 | CEMO/Adult/New Order/Verified address/ GPS determinate Sentence -add em (EMLV)/ GPS trail and EZ zone | 1. CEMO comes in 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10. Install | - Cemo new order api received - Case, mon, wo and wot created | 10 | 10 | Pass | to be sent by probation Need to discuss procedure for account and contact on ems case (keep Probation board but need to have email for contact or manually amend to correct probation region and email for contact) Install WOT0431032 MON10119168 |  | Calvin
CEMO19 | CEMO/Adult/New Order/Verified address/ GPS determinate Sentence -add em (EMLV)/ Curfew, GPS trail and AM | 1. CEMO comes in 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10. Create manual AM EMS case 11. Create MON, MONREQ and MONCON 12. Create WO and WOT | - Cemo new order api received - Case, mon, wo and wot created | 12 | 12 | Pass | to be sent by probation MON10119170 MON10119200 |  | Calvin
CEMO20 | CEMO/Adult/New Order/Verified address/ Determinate Sentence (EMLV)/Curfew | 1. CEMO comes in 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - Cemo new order api received - Case, mon, wo and wot created | 9 | 9 | Pass | to be sent by probation MON10119171 |  | Calvin
CEMO21 | CEMO/Adult/New Order/New Order/Verified Address/EDS (GPS Parole)/ GPS trail | 1. CEMO comes in 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - Cemo new order api received - Case, mon, wo and wot created | 9 | 9 | Pass | to be sent by probation MON10119172 |  | Calvin
CEMO22 | CEMO/Adult/New Order/Verified Address/DAPOL (late order from Probation - missed in error)/ GPS trail | 1. CEMO comes in 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - Cemo new order api received - Case, mon, wo and wot created | 9 | 9 | Pass | to be sent by probation MON10119188
CEMO23 | CEMO/Adult/New Order/Verified Address/GPS Dapol GPS Parole/RF & Exclusion/Inclusion - Curfew additional details & Offence Additional Details character length | 1. CEMO comes in 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order - check max 500 character length on curfew additional details and offence additional details 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | Able to save 500 characters on the CEMO MO form | 5 | 5 | Pass | Had to manually input as CEMO team confirm that the limit currently for offence additional details is still 100. Curfew and offence details are still using the old limits Was meant to check on CEMO MO Form which does have 500 character limit | STRY0085010 | Calvin

## AcquisitiveCrime
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Test Data Used | Executed By | Approved By
CEMOAC01 | Adult/CEMO New Order/Verified address/GPS Acquisitive Crime HDC/RF & Trail | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. create Work Order Task | - interaction, case, mon order, work order and work order task created | 9 | 9 | Pass | IAS MON10119230 |  | Calvin
CEMOAC02 | Adult/CEMO New Order/Verified address/GPS Acquisitive Crime Parole/Trail | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. create Work Order Task 10. install solo and phone | - interaction, case, mon order, work order and work order task created - devices installed, mon order live | 10 | 10 | Pass | IAS phone and solo MON10119232 WOT0431088 installed
CEMOAC03 | Adult/CEMO New Order/Verified address/GPS Acquisitive Crime Parole/Trail (late order from probation) | 1. CEMO comes in 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created - devices installed, mon order live | 10 | 10 | Pass | Install - WOT0431043 MON10119169 installed
Column1

## Variations
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Test Data Used
CEMOVAR01 | SR04 - Address Variation on CEMO06 | 1. CEMO for SR04 comes in 2.check cemo devwr and mon order forms 3. update DEVWR 4.update case 5. add moncon 6. Create WO 7. Create WOT 8. Install | - cemo new order APi received - SR04 ems case created - Enough info on ems case that gets created | 8 | 8 | Pass | Do after CEMO06. Need PW. Sent by probation EMS13539582 - WOT0431121 | STRY0082724
CEMOVAR02 | SR04 - Address Variation on community order | 1. Manually create interaction for community order curfew/GPS/ AM 2.Create EMS case 3.Create Mon,moncon, monreq 4. Create WO and WOT 5. Install 6. CEMO for SR04 comes in 7. Check cemo devwr and mon order forms 8. Update DEVWR 9. Update Case 10. Add moncon 11. Create WO and WOT 12. Install | - cemo new order APi received - SR04 ems case created - Enough info on ems case that gets created | 12 | 12 | Pass | See CEMOVAR03 for further test Sent in by probation MON10119233 AM - no wot needed MON10119226 curfew+GPS - WOT0431093
CEMOVAR03 | SR10 - Garden Access on community order | 1. CEMO for SR10 comes in 2. check cemo devwr and mon order forms 3. update devwr 4. update case 5. Create WO 6. Create WOT. | - cemo new order APi received - SR10 ems case created - Enough info on ems case that gets created | 6 | 6 | Pass | To be done after CEMOVAR02. May have to be sent in as SR08 and manually amend to SR10 Sent in by probation EMS13532296 - WOT0431094
CEMOVAR04 | SR04 - Add GPS to RF on CEMO17 | 1. CEMO for SR04 comes in 2.check cemo devwr and mon order forms 3. update DEVWR 4.update case 5. add monreq and moncon 6. Create WO 7. Create WOT 8. Install | - cemo new order APi received - SR04 ems case created - Enough info on ems case that gets created | 8 | 8 | Pass | Sent by YCS Book off as inability to monitor WOT0431126
CEMOVAR05 | SR10 - Equipment from GPS to RF on CEMO17 | 1. CEMO for SR04 comes in 2.check cemo devwr and mon order forms 3. update DEVWR 4.update case 5. deactivate monreq and moncon 6. Create WO 7. Create WOT 8. Install | - cemo new order APi received - SR04 ems case created - Enough info on ems case that gets created | 8 | 8 | Pass | Sent by YCS EMS13540604
CEMOVAR06 | SR04 - add curfew to GPS on CEMO18 | 1. CEMO for SR04 comes in 2.check cemo devwr and mon order forms 3. update DEVWR 4.update case 5. add monreq and moncon 6. Create WO 7. Create WOT 8. Install | - cemo new order APi received - SR04 ems case created - Enough info on ems case that gets created | 8 | 8 | Pass | Sent by probation EMS13533309 | today
CEMOVAR07 | SR08 - remove RF from GPS on CEMO18 | 1. CEMO for SR08 comes in 2.check cemo devwr and mon order forms 3. update DEVWR 4.update case 5. deactivate monreq and moncon | - cemo new order APi received - SR08 ems case created - Enough info on ems case that gets created | 5 | 5 | Pass | Sent by probation EMS13533343 | today
CEMOVAR08 | SR05 - 2nd address on CEMO17 | 1. CEMO for SR05 comes in 2.check cemo devwr and mon order forms 3. update DEVWR 4.update case 5. add moncon 6. Create WO 7. Create WOT 8. Install | - cemo new order APi received - SR05 ems case created - Enough info on ems case that gets created | 8 | 8 | Pass | Sent by YCS Not a CEMO issue but an install issue EMS13539602
CEMOVAR09 | SR08 - HV on CEMO18 | 1. CEMO for SR08 comes in 2.check cemo devwr and mon order forms 3.update case 4. update curfew hours | - cemo new order APi received - SR08 ems case created - Enough info on ems case that gets created | 4 | 4 | Pass | Sent by probation EMS13533330 | today
CEMOVAR10 | SR08 - Add EZ to GPS trail on CEMO18 | 1. CEMO for SR08 comes in 2.check cemo devwr and mon order forms 3.update case 4. Add EZ monreq and moncon | - cemo new order APi received - SR08 ems case created - Enough info on ems case that gets created | 4 | 4 | Pass | Sent by probation EMS13533346 - did as same time as CEMOVAR14 | today
CEMOVAR11 | SR21 - revocation of CEMO18 | 1. CEMO for SR21 comes in 2. check cemo devwr and mon order forms 3. Update case 4. Run playbook 5. Amend Mon order 6. Create WO and WOT | - cemo new order APi received - SR21 ems case created - Enough info on ems case that gets created | 6 | 6 | Pass | Sent by probation SR21 playbook not appearing but workaround of doing it manually is fine EMS13535511 | today
CEMOVAR12 | SR11 - End Bail | 1. CEMO for SR11 comes in 2. check cemo devwr and mon order forms 3. Update case 4. Amend 5. Amend Mon order 6. Create WO and WOT | - cemo new order APi received - SR11 ems case created - Enough info on ems case that gets created | 6 | 6 | Out of Scope | SR11 is not part of Phase 5 - this is part of later phase for MoJ
CEMOVAR13 | SR08 - Add AML on CEMO018 | 1. CEMO for SR08 comes in 2.check cemo devwr and mon order forms 3. update DEVWR 4.update case 5. Create case for AM MON 6. Create MON, Monreq and moncon 7. Create WO 8. Create WOT 9. Install | - cemo new order APi received - SR08 ems case created - Enough info to create AM Mon | 9 | 9 | Pass | Sent by probation EMS13535482 (cemo variation) EMS13535490 / MON10119263 (for creating AM order)
CEMOVAR14 | SR08 extend end date by 1 month on CEMO018 | 1. CEMO for SR08 comes in 2.check cemo devwr and mon order forms 3. update DEVWR 4.update case 5. extend order | - cemo new order APi received - SR08 ems case created - Enough info on ems case that gets created | 5 | 5 | Pass | EMS13533346 - did as same time as CEMOVAR10 | today
CEMOVAR15 | SR08 - remove EZ from CEMO18 | 1. CEMO for SR08 comes in 2.check cemo devwr and mon order forms 3. update DEVWR 4.update case 5. deactivate monreq and moncon | - cemo new order APi received - SR08 ems case created - Enough info on ems case that gets created | 5 | 5 | Pass | EMS13533343

## Sheet 4
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Test Data Used | Executed By | Approved By

## Validation (hidden)
Pass
Fail
No Run
Not Completed
In Progress
Out of Scope
Development
Blocked
Not Started

## Defects
Incident / JIRA ref | Test ID | Issue | Description | Category | Impact Rating (H-M-L) | Date Opened | Date Resolved | Target Release Date | Status | Post Production Check Y/N | Resolution | Release | Notes
1 | CEMO01 | createMO/updateMO endpoint data type for 'result' field has changed from an array to an object. |  |  | H | 2026-01-05 | 2026-01-05 |  | Ready for Prod | N | retested MoJ CEMO team can now sent DW and MON APIs |  | DFCT0011474
2 | CEMO01 | British Sign not pulling through - CEMO ISSUE & THEY ARE AWARE |  | CEMO - Phase 5 | H | 2026-01-06 | 2026-01-12 |  | Ready for Prod | N | retested and CEMO team can send langauge British Sign to us now |  | CEMO ISSUE NOT UP3
3 | CEMO01 | Addresses do not populate on curfew moncons in a scenario where the DW has 3x addresses | CEMO order for DW with 3x addresses - only 1 moncon had an address populated | CEMO - Phase 5 | H | 2026-01-06 | 2026-01-20 |  | Closed Complete | N |  |  | DFCT0011479
4 | CEMO01 | Disabilities not pulling through to Device Wearer form | CEMO form sent over with a list of disabilities - the list has not pulled through to the device wearer form | CEMO - Phase 5 | H | 2026-01-06 | 2026-01-28 |  | Ready for Prod | N | retested 26/01 Adult now ok but Child not pulling any disabilities through retested 28/01 now ok for adult and child |  | DFCT0011480
5 | CEMO01 | EMS Case state not updating to 'Awaiting Validation' | The state of CEMO monitoring order case has not updated to 'Awaiting Validation' - remains as 'Open' | CEMO - Phase 5 | H | 2026-01-07 | 23/01/2026 |  | Ready for Prod | N | replied back to UP3 as this was raised on a previous defect and it was fixed - DFCT0010940 MISSING STEP - CONTACT NUMBER |  | DFCT0011484
6 | CEMO01 | Update Device Wearer playbook step does not update device wearer when they have 3x addresses | CEMO Device Wearer form has 3x addresses for the device wearer but when completing the Update Device Wearer playbook step, the device wearer does not populate | CEMO - Phase 5 | H | 2026-01-07 | 2026-01-15 |  | Ready for Prod | N | retested now ok |  | DFCT0011486
7 | CEMO016 | NO_name not populated for youth orders (CEMO team issue) | CEMO team confirmed that they misunderstood a request and thought we no longer need YCS NO_name but we do. Story has been put in to add that requirement back in | CEMO - Phase 5 | H | 2026-01-07 | 14/01/2026 |  | Complete | N | CEMO12 has screenshots |  | CEMO ISSUE NOT UP3
8 | CEMO23 | Offence Additional Details and Curfew Additional Details data fields have not been updated to 500 characters. | Offence Additional Details is still 100 Curfew Additional Details is still 250 | CEMO - Phase 5 | H | 2026-01-08 | 2026-01-09 |  | Training | N | max character increase applies to CEMO forms not on servicenow forms |  | DFCT0011494
9 |  | Exclusion zone field appears to be in a different format - query raised | Exclusion zone field previously was in a text format - field is now in a code format | CEMO - Phase 5 | H | 2026-01-09 | 2026-01-15 |  | Ready for Prod | N | retested now ok |  | DFCT0011499
10 |  | new order received field not populating on cemo monitoring order form | New order received field should auto populate when the cemo case is created - new order received field not populating | CEMO - Phase 5 | M | 2026-01-09 | 20/01/2026 |  | Ready for Prod | N | UP3 advised empty on API - needs to be populated - data field is on JSON file |  | DFCT0011500
11 |  | Risk category (Disability concerns) not populating on CEMO device wearer form | CEMO form sent with risk category of Disability Concerns - CEMO device wearer form is missing this on the risk categories | CEMO - Phase 5 | M | 2026-01-09 | 2026-01-15 |  | Ready for Prod | N | retested now ok |  | DFCT0011501
12 |  | CEMO MoJ team have received failed to submit with one of the test scenarios - system returned a 500 error. |  | CEMO - Phase 5 | H | 2026-01-09 | 2026-01-16 |  | Ready for Prod | N | retested now ok |  | DFCT0011504
13 | CEMOVAR02 | CEMO team issue - unable to provide court case reference number | Bing confirmed that they are working on it | CEMO - Phase 5 | M | 2026-01-12 |  |  | On Hold |  | 14/01 spoke to Lisa, Crown Court & Magistrates Court Case Reference number fields can be sent by CEMO now. However on CEMO there is a data field called court case reference number which then maps to the correct data field 20/01 CL spoke to Lisa, Confirmed ability to send crown court case ref number is being worked on this sprint 21/01 Magistrates tested - Crown in Phase 6 sprint development |  | CEMO ISSUE NOT UP3
14 | CEMOVAR02 | Account & Contact not auto-populating - CEMO variations | Account & Contact fields in the SR04 case aren't auto populating | CEMO - Phase 5 | H | 2026-01-12 | 2026-01-15 |  | Ready for Prod | N | retested now ok |  | DFCT0011506
15 | CEMOVAR02 | Condition Type not populating on CEMO Monitoring Order | Condition Type not populating on CEMO Monitoring Order as being sent 'Requirement of a Community Order' | CEMO - Phase 5 | H | 2026-01-12 | 2026-01-30 |  | Complete | N | Retested 30/01 - now ok 19/01 Dfct closed - issue with MoJ team - change raised for them to amend to ‘Requirement of Community Order’ |  | DFCT0011507 CEMO ISSUE NOT UP3
16 | All updates | PREPROD - CEMO UPDATES - 500 ERROR BEING RETURNED | raised by MOJ TEAM | CEMO - Phase 5 | H | 2026-01-15 | 2026-01-21 |  | Ready for Prod | N | retested now ok |  | DFCT0011512
17 |  | Account & Contact not auto-populating - new CEMO orders | Account & Contact fields in a new monitoring case aren't auto populating | CEMO - Phase 5 | H | 16/01/2026 | 2026-01-16 |  | Ready for Prod | N | retested now ok |  | DFCT0011513
18 |  | SR21 cases are not generating a playbook | SR21s not generating a playbook even if you populate some of the fields and save the case - playbook appears when we create manual SR21 cases | CEMO - Phase 5 | H | 16/01/2026 | 2026-01-19 |  | Training | N | 19/01 CL & ML agreed playbook not required for CEMO SR21 - to update SOPs |  | DFCT0011514
19 |  | IAS tickbox. Manual ticking is fine but CEMO team have not done the story | Bing has said that that is on a backlog and most likely to start development from 03/02 | CEMO - Phase 5 | M | 2026-01-16 |  |  | On Hold | N | Part of Phase 6 - ops to continue with manual process until Phase 6 |  | CEMO ISSUE NOT UP3
20 |  | Conditional release time not populating on the CEMO MO form | Conditional release times not populating on the CEMO MO form despite being on the json | CEMO - Phase 5 | L | 19/01/2026 | 2026-01-19 |  | Training | N | DMND0001368 Misc Cemo Enhancements has already been raised for the Conditional time fields to be populated on the Cemo form. The date is currently populated on the Cemo form. raised for future enhancement WORKAROUND - agent can retrieve data from json text info |  | DFCT0011518
21 | CEMOVAR04 | SR04 sent with disability selected but 500 error message being received. |  | CEMO - Phase 5 | H | 2026-01-19 |  |  | Cancelled |  | UP3 requested retest of SR04 retested now ok |  | DFCT0011520
22 | CEMO17 | Offence option misspelt on Service Now Mon Order form |  | CEMO - Phase 5 | H | 2026-01-19 | 23/01/2026 |  | Ready for Prod |  |  |  | DFCT0011524 RITM1726138
23 |  | risk form being sent before devwr gets created |  | CEMO - Phase 5 | M | 2026-01-21 | 2026-01-28 |  | Prod INC | N | inc - CL emailed OE Managers to raise as an INC |  | INC1755608
24 |  | SR08 Order Variation Type not populating on ServiceNow, some options missing on json file and some options don't match DDV6 |  | CEMO - Phase 5 | L | 2026-01-26 |  |  | Open | N | workaround - ops to manually update OVT on ServiceNow - full solution in March release |  | DFCT0011542
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
6.1.25
Note on J1: Barlow, Beverley (UK & Europe): Open, Fixed, Retest, Training, Closed

## Sheet1 (hidden)
Testing Timeline
| 19th |  | 20th |  | 21st | 24th | 25th | 26th | 27th | 28th
ST | OE44 * Install alcohol kit | ST | DV50 * Asset Manager BPSS persona | ST | DV50 * Asset Manager BPSS persona
KW | DV41 * Field Service Officer persona | ST | DV51 * Asset Manager CTC persona | ST | DV51 * Asset Manager CTC persona
KW | DV42 * Field Service Officer SPECIALS persona | ST | DV21 * Field Service Scheduler BPSS persona | ST | DV21 * Field Service Scheduler BPSS persona
LJ | DV44 * Quality Assurance CTC persona | ST | DV22 * Field Service Scheduler CTC persona | ST | DV22 * Field Service Scheduler CTC persona
EM | DV48 * CMT Immigration persona FAILED | TL / MHI | TA08 * atv breaches |  | TA31
EM | DV49 * CMT (MoJ) personas PASSED | ST | OEO7 * install following OE01 decom |  | TA10 / OE70
ST | OE69 * install NFD | EM | TA04 *EXCLUSION | EM | TA04 *EXCLUSION
EM | TA09 / OE69 * start the AL18 process | EM | TA30 *AL15 | EM | TA30 *AL15
TL / MHI | TA01 / OE01 * finish generating the atvs & breach packs | EM | TA47 * AL24 -SPOOF | EM | TA47 * AL24 -SPOOF
TL / MHI | TA52 / OE01 * generate AL04 | LJ | TA48 * AL20 |  | OE06
ST | TA43 / OE01 * request spoof event from AUEM | LJ | OE04 * check further visit has generated after previous visit booked off as faulty equipment |  | OE76
ST | OE01 * decom kit once event has been spoofed | ST | OE01 * decom kit |  | OE08
EM / ST & KW | OE04 * Create order * Assign WOT to Mark * 2x no show visits | ST | OE03 * 2x no show |  | TA41
ST & KW | OE03 * Assign WOT to Mark * 2x no show visits | TL / MHI | TA02 * 2x no show breach |  | OE09 | NO SHOW
TL / MHI | TA05 / OE02 * Create multiple exclusions Day 1 | TL / MHI | TA05 / OE02 * Create multiple exclusions Day 2 |  | OE10 | BOOK OFFS
TL / MHI & ST | TA11 / OE02 * Generate strap tamper * Complete tamper visit | TL / MHI | TA46 * breach |  | OE15
TL / MHI | TA33 / OE20 * battery dead | ST | TA03 * 2x no show |  | OE16
MS | OE08 * Create order | TL / MHI | TA03 * breach |  | OE17
MS | OE09 * Create order | ST | OE11 * 2x no show |  | OE12
MS | OE10 * Create order | TL / MHI | TA13 * breach |  | OE13
MS | OE11 * Create order | LJ | TA68 * breach | LJ | TA68 * breach
MS | OE12 * Create order | EM | OE18 * decom
MS | OE13 * Create order | MS | OE15 * create order
CL | OE45 * Create order | MS | OE16 * create order
CL | OE46 * Create order | MS | OE17 * create order
CL | OE47 * Create order | MS | OE19 * create order
ST | OE14 * decom kit | MS | OE21 * create order
ST | OE20 * install kit | MS | OE22 * create order
TL / MHI | TA08 * start atv breaches | MS | OE23 * create order
|  | MS | OE24 * create order
|  | MS | OE25 * create order
|  | MS | OE26 * create order | MS | OE26 * create order
|  | MS | OE27 * create order
|  | MS | OE28 * create order | MS | OE28 * create order
|  | CL | OE29 * create order | MS | OE29 * create order
|  | CL | OE30 * create order | MS | OE30 * create order
|  | CL | OE31 * create order | MS | OE31 * create order
|  | CL | AC01 * create order | CL | AC01 * create order
|  | CL | AC02 * create order | CL | AC02 * create order
|  | CL | AC03 * create order | CL | AC03 * create order
|  | CL | AC04 * create order | CL | AC04 * create order
|  | LJ | DV41 * Field Service Officer persona
|  | LJ | DV42 * Field Service Officer SPECIALS persona
|  | LJ | TA40 * once the 2x no shows are complete - create a new installation work order
|  | ST | TA40 * threatening words & behaviour
|  | LJ | TA40 * breach
|  | TL / MHI | TA58 * aggregation
|  | TL / MHI | TA59 * aggregation
|  | TL / MHI | TA60 * aggregation |  | TA60 * aggregation
|  | TL / MHI | TA61 * aggregation |  | TA61 * aggregation
|  | TL / MHI | TA62 * aggregation |  | TA62 * aggregation
|  | ST | TA46 * 1x threatening words & behaviour
|  | EM | TA46 * breach
|  | LJ | OE49
|  | LJ | OE50

## OVERALL
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Issue/Defect | SERCO JIRA ID | SNOW defect ID | Approved By