## Version Control
Document Information
Title | Test Execution Progress Log
Title | Feb Release - KPI6 & KPI9
Release Identifier | RLSE0010173
Author | Beverley Barlow
Document Version History
Version | Date | Summary of Changes
0.1 | 2026-05-01 | Initial Definition of Test Cases
0.2 | 2026-01-31 | Final Issue for MOJ review
Test Evidence Repository
Test Execution Evidence is stored at this link |  | Link to Test Evidence Repository
Scope of Release
This release implements a Servicenow upgrade
Defect/Story ID | Type | Details
STRY0084586 | Enhancement | New field to be added on the Interaction Import table, to accurately record the right time / date of the call being made.
STRY0085055 | Enhancement | KPI 6 call made field and the first response time field will be populated with the data in the call_date_time field from the Interaction import table
STRY0085783 | Enhancement | Interaction Import record should not raise an interaction if state = Not Answered
STRY0086362 | Enhancement | Breach pack sent to RO to become mandatory
STRY0086547 | Enhancement | Hiding the propose solution UI action on enforcement cases

## Summary
|  |  | ORDERS DASHBOARD |  |  |  | SHEET4 DASHBOARD |  |  |  | OVERALL DASHBOARD
Execution Progress |  |  |  | Execution Progress |  |  |  | Execution Progress
Steps Completed | 90 |  |  | Steps Completed | 0 |  |  | Steps Completed | 0
Steps Remaining | 0 |  |  | Steps Remaining | 0 |  |  | Steps Remaining | 0
Total Steps | 90 |  |  | Total Steps | 0 |  |  | Total Steps | 0
% Complete | 100% |  |  | % Complete | #NAME? |  |  | % Complete | #DIV/0!
Script Status |  |  |  | Script Status |  |  |  | Script Status
Pass | 9 | 100% |  | Pass | 0 | #DIV/0! |  | Pass | 0 | #DIV/0!
Fail | 0 | 0% |  | Fail | 0 | #DIV/0! |  | Fail | 0 | #DIV/0!
No Run | 0 | 0% |  | No Run | 0 | #DIV/0! |  | No Run | 0 | #DIV/0!
Not Completed | 0 | 0% |  | Not Completed | 0 | #DIV/0! |  | Not Completed | 0 | #DIV/0!
In Progress | 0 | 0% |  | In Progress | 0 | #DIV/0! |  | In Progress | 0 | #DIV/0!
Out of Scope | 0 | 0% |  | Out of Scope | 0 | #DIV/0! |  | Out of Scope | 0 | #DIV/0!
Not Started | 0 | 0% |  | Not Started | 0 | #DIV/0! |  | Not Started | 0 | #DIV/0!
TOTAL | 9 |  |  | TOTAL | 0 |  |  | TOTAL | 0
|  |  | SHEET3 DASHBOARD |  |  | KPI6 DASHBOARD
Execution Progress |  |  |  | Execution Progress
Steps Completed | 0 |  |  | Steps Completed | 513
Steps Remaining | 0 |  |  | Steps Remaining | 0
Total Steps | 0 |  |  | Total Steps | 513
% Complete | #DIV/0! |  |  | % Complete | 100%
Script Status |  |  |  | Script Status
Pass | 0 | #DIV/0! |  | Pass | 61 | 59.22%
Fail | 0 | #DIV/0! |  | Fail | 0 | 0%
No Run | 0 | #DIV/0! |  | No Run | 0 | 0%
Not Completed | 0 | #DIV/0! |  | Not Completed | 0 | 0%
In Progress | 0 | #DIV/0! |  | In Progress | 0 | 0%
Out of Scope | 0 | #DIV/0! |  | Out of Scope | 42 | 40.78%
Not Started | 0 | #DIV/0! |  | Not Started | 0 | 0%
TOTAL | 0 |  |  | TOTAL | 103

## Orders
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Test Data Used | Executed By | Approved By | Tests to do
KO01 | Adult - New Order - Verified Address - GPS Bail-Curfew only | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass | DEVWR0101676 / MON10119207 |  | Luke |  | KP04 KP05 KP06 KP10 KP11 KP12 KP13 KP14 KP15 KP16 KP17 KP18
KO02 | Adult - New Order - Verified Address - GPS Bail- Location | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass | DEVWR0101679 / MON10119208 |  | Luke |  | KP01 KP02 KP03 KP07 KP08 KP09
KO03 | Adult - New Order - Verified Address - GPS Bail-Curfew and Location | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass | DEVWR0101684-MON10119211 |  | Luke |  | KP19 KP20 KP21 KP22 KP23 KP24 KP25 KP26 KP27 KP28 KP29 KP30
KO04 | Adult-Non-Bail-Community-curfew | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass | DEVWR0101691 / MON10119213 |  | Luke |  | KP32 KP33 KP34 KP44 KP45 KP46 KP47 KP48 KP49
KO05 | Adult-Non-Bail-Post Release- location | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass | DEVWR0101694 / MON10119216 |  | Luke |  | KP35 KP36 KP37 KP38 KP39 KP40 KP41 KP42
KO06 | Adult-Non-Bail-Post Release- Curfew and Location | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass | DEVWR0101702 / MON10119224 |  | Luke |  | KP49 KP50 KP51 KP51 KP52 KP53 KP54 KP55 KP56 KP57 KP58 KP59 KP60 KP61
KO07 | Immigration-GPS-CURFEW | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass | DEVWR0101714 / MON10119231 |  | Luke |  | KP65 KP66 KP67 KP74 KP75 KP76 KP77 KP78 KP79
KO08 | Immigration-GPS-LOCATION | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass | DEVWR0101719 / MON10119238 |  | Luke |  | KP62 KP63 KP64 KP68 KP69 KP70 KP71 KP72 KP73
K009 | Immigration-GPS-Location and curfew | 1. create Interaction 2. create Contact 3. create Device Wearer 4. create Case 5. create Monitoring Order 6. create Monitoring Requirements 7. create Monitoring Configuration 8. create Work Order 9. Create Work Order Task 10. Install | - interaction, case, mon order, work order and work order task created | 10 | 10 | Pass | DEVWR0101726 / MON10119241 |  | Luke |  | KP80 KP81 KP82 KP83 KP84 KP85 KP86 KP87 KP88 KP89 KP90 KP91
Column1

## KPI6
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Data notes | Tested by | order used
KP01 | AL02-Bail - answered | AL02 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL02 Tamper of worn device non curfew order - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO02
KP02 | AL02-Bail - abandoned | AL02 has been created - API to PD displayed in activity stream - call made to HMU - listen to 50% of call then abandon call - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL02 Tamper of worn device non curfew order - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Call Abandoned - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO02
KP03 | AL02-Bail - not answered | AL02 has been created - API to PD displayed in activity stream - call made to HMU - call not answered - update investigation outcome field to Violation confirmed - update resolution field to completed - update state to resolved | - API to PD displayed in activity stream - auto set first response date and time field in table - First Call Outcome data field populated on case - no interaction created - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved" | 8 | 8 | Pass |  |  |  | KO02
KP04 | AL03-Bail - answered | AL03 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL03 Tamper of worn device (curfew order) - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO01
KP05 | AL03-Bail - abandoned | AL03 has been created - API to PD displayed in activity stream - call made to HMU - listen to 50% of call then abandon call - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL03 Tamper of worn device (curfew order) - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Call Abandoned - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO01
KP06 | AL03-Bail - not answered | AL03 has been created - API to PD displayed in activity stream - call made to HMU - call not answered - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | - API to PD displayed in activity stream - auto set first response date and time field in table - First Call Outcome data field populated on case - needs attention flag updated on case - no interaction created - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 7 | 7 | Pass |  |  |  | KO01
KP07 | AL04-Bail - answered | AL04 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL04 Power off of Curfew Monitoring Equipment - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO02
KP08 | AL04-Bail - abandoned | "AL04 has been created - API to PD displayed in activity stream - call made to HMU - listen to 50% of call then abandon call - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL04 Power off of Curfew Monitoring Equipment - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Call Abandoned - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO02
KP09 | AL04-Bail - not answered | AL04 has been created - API to PD displayed in activity stream - call made to HMU - call not answered - update investigation outcome field to Violation confirmed - update resolution field to completed - update state to resolved | - API to PD displayed in activity stream - auto set first response date and time field in table - First Call Outcome data field populated on case - no interaction created - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved" | 8 | 8 | Pass |  |  |  | KO02
KP10 | AL05-Bail - answered | AL05 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | - API to PD displayed in activity stream - auto set first response date and time field in table - First Call Outcome data field populated on case - no interaction created - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved" | 8 | 8 | Pass |  |  |  | KO01
KP11 | AL05-Bail - abandoned | AL05 has been created - API to PD displayed in activity stream - call made to HMU -Interaction created in ServiceNow with Short description: AL02 Tamper of worn device (non-curfew order) -Listen to 50% of call-Call Adbandoned - call ends - interaction closed - auto set first response date and time field -investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved -save -run KPI 6 report -Produce Breach Pack | "- interaction created as WIP - auto set first response date and time field breach pack to send to RO mandatory | 14 | 14 | Pass |  |  |  | KO01
KP12 | AL05-Bail - not answered | AL05 has been created - API to PD displayed in activity stream - call made to HMU - call not answered - update investigation outcome field to Violation confirmed - update resolution field to completed - update state to resolved | - API to PD displayed in activity stream - auto set first response date and time field in table - First Call Outcome data field populated on case - no interaction created - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved" | 8 | 8 | Pass |  |  |  | KO01
KP13 | AL08-Bail - answered | AL08 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL08 Out Past Curfew Commencement - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO01
KP14 | AL08-Bail - abandoned | "AL08 has been created - API to PD displayed in activity stream - call made to HMU -Interaction created in ServiceNow with Short description: AL02 Tamper of worn device (non-curfew order) -Listen to 50% of call-Call Adbandoned - call ends - interaction closed - auto set first response date and time field -investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved -run KPI 6 report | "- interaction created as WIP - auto set first response date and time field breach pack to send to RO mandatory | 12 | 12 | Pass |  |  |  | KO01
KP15 | AL08-Bail - not answered | AL08 has been created - API to PD displayed in activity stream - call made to HMU - call not answered - update investigation outcome field to Violation confirmed - update resolution field to completed - update state to resolved | - API to PD displayed in activity stream - auto set first response date and time field in table - First Call Outcome data field populated on case- no interaction created - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved" | 8 | 8 | Pass |  |  |  | KO01
KP16 | AL10-Bail - answered | AL10 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL10 Left home during Curfew - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO01
KP17 | AL10-Bail - abandoned | "AL10 has been created - API to PD displayed in activity stream - call made to HMU - listen to 50% of call then abandon call - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL10 Left home during Curfew - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Call Abandoned - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO01
KP18 | AL10-Bail - not answered | AL10 has been created - API to PD displayed in activity stream - call made to HMU - call not answered - update investigation outcome field to Violation confirmed - update resolution field to completed - update state to resolved | - API to PD displayed in activity stream - First Call Outcome data field populated on case- no interaction created - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved" | 8 | 8 | Pass |  |  |  | KO01
KP19 | AL19-Bail - answered | AL19 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL19-Missing Status Check - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | Tested as part of KP102
KP20 | AL19-Bail - abandoned | AL19 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL19-Missing Status Check -Listen to 50% of call - call ends | - interaction created as WIP | 6 | 6 | Out of Scope | Tested as part of KP102
KP21 | AL19-Bail - not answered | AL19 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | Tested as part of KP102
KP22 | AL20- BAIL - answered | AL20 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL20 No movement of Device-Wearer - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO03
KP23 | AL20-BAIL - abandoned | AL20 has been created - API to PD displayed in activity stream - call made to HMU - listen to 50% of call then abandon call - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL20 No movement of Device-Wearer - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Call Abandoned - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO03
KP24 | AL20-BAIL- not answered | AL20 has been created - API to PD displayed in activity stream - call made to HMU - call not answered - update investigation outcome field to Violation confirmed - update resolution field to completed - update state to resolved | - API to PD displayed in activity stream - First Call Outcome data field populated on case - no interaction created - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved" | 8 | 8 | Pass |  |  |  | KO03
KP25 | AL21-Bail - answered | AL21 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL21-Non-charged Device Low Battery. Battery running low - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | AL21 not part of KPI6 - do not trigger PD calls
KP26 | AL21-Bail - abandoned | AL21 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL21-Non-charged Device Low Battery. Battery running low -Listen to 50% of call - call ends | - interaction created as WIP | 6 | 6 | Out of Scope | AL21 not part of KPI6 - do not trigger PD calls
KP27 | AL21-Bail - not answered | AL21 has been created - API to PD displayed in activity stream - call made to HMU -unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | AL21 not part of KPI6 - do not trigger PD calls
KP28 | AL22-BAIL - answered | AL22 has been created - API triggered to PD Battery Alert campaign - PD call made to HMU - call answered - call ends - on case select 'Violation confirmed' in Investigation Outcome field - set case state to resolved - insert text in Work notes (private) - insert Complete in Resolution code - insert text in Resolution notes - select Save | - API to PD displayed in activity stream - interaction created in ServiceNow with Short description: AL22 Automated voice message to Device Wearer - chat summary updated on interaction - interaction closed - case set to resolved and data fields updated | 11 | 11 | Pass |  |  |  | KO03
KP29 | AL22-BAIL - abandoned | AL22 has been created - API triggered to PD Battery Alert campaign - PD call made to HMU - call answered but abandon call after 50% of message heard - call ends - set interaction state to Closed Abandoned - on case select 'Violation confirmed' in Investigation Outcome field - set case state to resolved - insert text in Work notes (private) - insert Complete in Resolution code - insert text in Resolution notes - select Save | - API to PD displayed in activity stream - interaction created in ServiceNow with Short description: AL22 Automated voice message to Device Wearer - chat summary updated on interaction - interaction set to Work In Progress state - interaction updated to Closed Abandoned state - case set to resolved and data fields updated | 12 | 12 | Pass |  |  |  | KO03
KP30 | AL22- BAIL - not answered | AL22 has been created - API triggered to PD Battery Alert campaign - PD call made to HMU - call not answered - on case select 'Violation confirmed' in Investigation Outcome field - set case state to resolved - insert text in Work notes (private) - insert Complete in Resolution code - insert text in Resolution notes - select Save | - API to PD displayed in activity stream - no interaction created - unsuccessful work note added - needs attention flag updated on case - case set to resolved and data fields updated | 9 | 9 | Pass |  |  |  | KO03
KP31 | STRY0086547-Hiding the propose solution UI action on enforcement cases | Find EMS case make sure it is an open Case there shouldn't be a 'Propose solution'button | Then I will NO longer see the 'Propose Solution' button | 3 | 3 | Pass
KP32 | AL02-NON BAIL- answered | " AL02 has been created - API to PD displayed in activity stream - call made to HMU -call answered -Interaction created in ServiceNow with Short description: AL02 Tamper of worn device (non-curfew order) - call ends - interaction closed - auto set first response date and time field -investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved -run KPI 6 report | - auto set first response date and time field -manually investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 12 | 12 | Pass |  |  |  | KO04
KP33 | AL02-NON BAIL - abandoned | AL02 has been created - API to PD displayed in activity stream - call made to HMU -Interaction created in ServiceNow with Short description: AL02 Tamper of worn device (non-curfew order) -Listen to 50% of call - call ends - interaction closed - auto set first response date and time field -investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved -run KPI 6 report | - interaction created as WIP - auto set first response date and time field | 12 | 12 | Pass |  |  |  | KO04
KP34 | AL02-NON BAIL - not answered | AL02 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated -run KPI6 report auto set first response date and time field -investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | - auto set first response date and time field | 10 | 10 | Pass |  |  |  | KO04
KP35 | AL03-NON BAIL - answered | AL03 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL03 Tamper of worn device (curfew order) - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO05
KP36 | AL03-NON BAIL - abandoned | AL03 has been created - API to PD displayed in activity stream - call made to HMU - listen to 50% of call then abandon call - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL03 Tamper of worn device (curfew order) - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Call Abandoned - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO05
KP37 | AL03-NON BAIL - not answered | AL03 has been created - API to PD displayed in activity stream - call made to HMU - call not answered - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | - API to PD displayed in activity - auto set first response date and time field in table - First Call Outcome data field populated on case - needs attention flag updated on case - no interaction created - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO05
KP38 | AL04-NON BAIL- answered | AL04 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL04 Power off of Curfew Monitoring Equipment - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO05
KP39 | AL04-NON BAIL - abandoned | "AL04 has been created - API to PD displayed in activity stream - call made to HMU - listen to 50% of call then abandon call - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL04 Power off of Curfew Monitoring Equipment - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Call Abandoned - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO05
KP40 | AL04-NON BAIL - not answered | AL04 has been created - API to PD displayed in activity stream - call made to HMU - call not answered - update investigation outcome field to Violation confirmed - update resolution field to completed - update state to resolved | - API to PD displayed in activity - auto set first response date and time field in table - First Call Outcome data field populated on case - no interaction created - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved" | 8 | 8 | Pass |  |  |  | KO05
KP41 | AL05-NON BAIL - answered | AL05 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL05 Movement of Home Monitoring Unit - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO05
KP42 | AL05-NON BAIL - abandoned | AL05 has been created - API to PD displayed in activity stream - call made to HMU -Interaction created in ServiceNow with Short description: AL02 Tamper of worn device (non-curfew order) -Listen to 50% of call-Call Adbandoned - call ends - interaction closed - auto set first response date and time field -investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved -save -run KPI 6 report -Produce Breach Pack | "- interaction created as WIP - auto set first response date and time field breach pack to send to RO mandatory | 14 | 14 | Pass |  |  |  | KO05
KP43 | AL05-NON BAIL - not answered | "AL05 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated -run KPI6 report auto set first response date and time field -investigation outcome field set to Violation confirmed - resolution field set to completed - state set to Closed -save -produce Breach Pack -Run KPI6 report " | breach pack to send to RO mandatory Auto set first response date and time field | 13 | 13 | Pass |  |  |  | KO05
KP44 | AL08-NON BAIL - answered | AL08 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL08 Out Past Curfew Commencement - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO04
KP45 | AL08-NON BAIL - abandoned | "AL08 has been created - API to PD displayed in activity stream - call made to HMU -Interaction created in ServiceNow with Short description: AL02 Tamper of worn device (non-curfew order) -Listen to 50% of call-Call Adbandoned - call ends - interaction closed - auto set first response date and time field -investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved -run KPI 6 report | "- interaction created as WIP - auto set first response date and time field breach pack to send to RO mandatory | 12 | 12 | Pass |  |  |  | KO04
KP46 | AL08-NON BAIL - not answered | "AL08 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated auto set first response date and time field -investigation outcome field set to Violation confirmed - resolution field set to completed - state set to Closed -Run KPI6 report " | - auto set first response date and time field | 10 | 10 | Pass |  |  |  | KO04
KP47 | AL10-NON BAIL - answered | AL10 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL10 Left home during Curfew - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO04
KP48 | AL10-NON BAIL - abandoned | "AL10 has been created - API to PD displayed in activity stream - call made to HMU -Interaction created in ServiceNow with Short description: AL02 Tamper of worn device (non-curfew order) -Listen to 50% of call-Call Adbandoned - call ends - interaction closed - auto set first response date and time field run KPI 6 report -investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | "- interaction created as WIP - auto set first response date and time field breach pack to send to RO mandatory | 12 | 12 | Pass |  |  |  | KO04
KP49 | AL10-NON BAIL - not answered | "AL10 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated auto set first response date and time field -investigation outcome field set to Violation confirmed - resolution field set to completed - state set to Closed -Run KPI6 report " | - auto set first response date and time field | 10 | 10 | Pass |  |  |  | KO04
KP50 | AL19-NON BAIL - answered | AL19 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL19-Missing Status Check - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | Tested as part of KP103
KP51 | AL19-NON BAIL - abandoned | AL19 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL19-Missing Status Check -Listen to 50% of call - call ends | - interaction created as WIP | 6 | 6 | Out of Scope | Tested as part of KP103
KP52 | AL19-NON BAIL - not answered | AL19 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | Tested as part of KP103
KP53 | AL20-NON BAIL - answered | AL20 has been created - API to PD displayed in activity stream - call made to HMU - call answered - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved | -Interaction created in ServiceNow with Short description: AL20 No movement of Device-Wearer - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 8 | 8 | Pass |  |  |  | KO06
KP54 | AL20-NON BAIL - abandoned | AL20 has been created - API triggered to PD Non compliance campaign - PD call made to HMU - call answered - update interaction chat summary & abandon call after 50% of message heard - call ends - set interaction state to Closed Abandoned - on case select 'Violation confirmed' in Investigation Outcome field - set case state to resolved - insert text in Work notes (private) - insert Complete in Resolution code - insert text in Resolution notes - select Save | - API to PD displayed in activity stream - interaction created - chat summary updated on interaction - interaction set to Work In Progress state - interaction updated to Closed Abandoned state - case set to resolved and data fields updated | 13 | 13 | Pass |  |  |  | KO06
KP55 | AL20-NON BAIL - not answered | AL20 has been created - API triggered to PD Battery Alert campaign - PD call made to HMU - call not answered - on case select 'Violation confirmed' in Investigation Outcome field - set case state to resolved - insert text in Work notes (private) - insert Complete in Resolution code - insert text in Resolution notes - select Save | - API to PD displayed in activity stream - no interaction created - case set to resolved and data fields updated | 10 | 10 | Pass |  |  |  | KO06
KP56 | AL21 -NON BAIL- answered | AL21 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL21-Non-charged Device Low Battery. Battery running low - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | AL21 not part of KPI6 - do not trigger PD calls
KP57 | AL21 -NON BAIL - abandoned | AL21 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL21-Non-charged Device Low Battery. Battery running low -Listen to 50% of call - call ends | - interaction created as WIP | 6 | 6 | Out of Scope | AL21 not part of KPI6 - do not trigger PD calls
KP58 | AL21 -NON BAIL - not answered | AL21 has been created - API to PD displayed in activity stream - call made to HMU -unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | AL21 not part of KPI6 - do not trigger PD calls
KP59 | AL22-NON BAIL - answered | AL22 has been created - API triggered to PD Battery Alert campaign - PD call made to HMU - call answered - call ends | - API to PD displayed in activity stream - interaction created in ServiceNow with Short description: AL22 Automated voice message to Device Wearer - chat summary updated on interaction - interaction closed - case set to resolved and data fields updated | 4 | 4 | Pass |  |  |  | KO06
KP60 | AL22-NON BAIL - abandoned | AL22 has been created - API triggered to PD Battery Alert campaign - PD call made to HMU - call answered but abandon call after 50% of message heard - call ends - set interaction state to Closed Abandoned - on case select 'Violation confirmed' in Investigation Outcome field - set case state to resolved - insert text in Work notes (private) - insert Complete in Resolution code - insert text in Resolution notes - select Save | - API to PD displayed in activity stream - interaction created in ServiceNow with Short description: AL22 Automated voice message to Device Wearer - chat summary updated on interaction - interaction set to Work In Progress state - interaction updated to Closed Abandoned state - case set to resolved and data fields updated | 12 | 12 | Pass |  |  |  | KO06
KP61 | AL22-NON BAIL - not answered | AL22 has been created - API triggered to PD Battery Alert campaign - PD call made to HMU - call not answered - on case select 'Violation confirmed' in Investigation Outcome field - set case state to resolved - insert text in Work notes (private) - insert Complete in Resolution code - insert text in Resolution notes - select Save | - API to PD displayed in activity stream - no interaction created - unsuccessful work note added - needs attention flag updated on case - case set to resolved and data fields updated | 9 | 9 | Pass |  |  |  | KO06
KP62 | AL02-Immigration - answered | " AL02 has been created - API to PD displayed in activity stream - call made to HMU -Interaction created in ServiceNow with Short description: AL02 Tamper of worn device (non-curfew order) - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS TESTED ON KP95
KP63 | AL02-Immigration - abandoned | AL02 has been created - API to PD displayed in activity stream - call made to HMU -Interaction created in ServiceNow with Short description: AL02 Tamper of worn device (non-curfew order) -Listen to 50% of call - call ends |  | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS TESTED ON KP95
KP64 | AL02-Immigration - not answered | AL02 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | IMMIGRATION DON'T GET PD CALLS TESTED ON KP95
KP65 | AL03-Immigration - answered | AL03 has been created - API to PD displayed in activity stream - call made to HMU - interaction created in ServiceNow with Short description: AL03-Tamper of worn device with curfew order - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS TESTED ON KP96
KP66 | AL03-Immigration - abandoned | AL03 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL03-Tamper of worn device with curfew order -Listen to 50% of call - call ends | - interaction created as WIP | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS TESTED ON KP96
KP67 | AL03-Immigration - not answered | AL03 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | IMMIGRATION DON'T GET PD CALLS TESTED ON KP96
KP68 | AL04-Immigration - answered | AL04 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL04-Power off of curfew monitoring equipment at home - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS TESTED ON KP97
KP69 | AL04-Immigration - abandoned | AL04 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL04-Power off of curfew monitoring equipment at home Listen to 50% of call - call ends | - interaction created as WIP | 5 | 5 | Out of Scope | IMMIGRATION DON'T GET PD CALLS TESTED ON KP97
KP70 | AL04-Immigration - not answered | AL04 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP97
KP71 | AL05-Immigration - answered | AL05 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL05-Movement of home monitoring unit at home - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP98
KP72 | AL05-Immigration - abandoned | AL05 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL05-Movement of home monitoring unit at home -Listen to 50% of call - call ends | - interaction created as WIP | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP98
KP73 | AL05-Immigration - not answered | AL05 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP98
KP74 | AL08-Immigration - answered | AL08 has been created - API to PD displayed in activity stream - call made to HMU - interaction created in ServiceNow with Short description: AL08-Out past curfew commencement - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS
KP75 | AL08-Immigration - abandoned | AL08 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL08-Out past curfew commencement -Listen to 50% of call - call ends | - interaction created as WIP | 3 | 3 | Out of Scope | IMMIGRATION DON'T GET PD CALLS
KP76 | AL08-Immigration - not answered | AL08 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | IMMIGRATION DON'T GET PD CALLS
KP77 | AL10-Immigration - answered | AL10 has been created - API to PD displayed in activity stream - call made to HMU - interaction created in ServiceNow with Short description: AL10-Left home during curfew - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS
KP78 | AL10-Immigration - abandoned | AL10 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL10-Left home during curfew Listen to 50% of call - call ends | - interaction created as WIP | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS
KP79 | AL10-Immigration - not answered | AL10 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | IMMIGRATION DON'T GET PD CALLS
KP80 | AL19-Immigration - answered | AL19 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL19-Missing Status Check - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP99
KP81 | AL19-Immigration - abandoned | AL19 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL19-Missing Status Check -Listen to 50% of call - call ends | - interaction created as WIP | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP99
KP82 | AL19-Immigration - not answered | AL19 has been created - API to PD displayed in activity stream - call made to HMU unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP99
KP83 | AL20-Immigration - answered | AL20 has been created - API to PD displayed in activity stream - call made to HMU interaction created in ServiceNow with Short description: AL20-No movement of Device-Wearer - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP100
KP84 | AL20-Immigration - abandoned | AL20 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL20-No movement of Device-Wearer -Listen to 50% of call - call ends | - interaction created as WIP | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP100
KP85 | AL20-Immigration - not answered | AL20 has been created - API to PD displayed in activity stream - call made to HMU -unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP100
KP86 | AL21 -Immigration - answered | AL21 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL21-Non-charged Device Low Battery. Battery running low - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS tested on KP101
KP87 | AL21 -Immigration - abandoned | AL21 has been created - API to PD displayed in activity stream - call made to HMU -interaction created in ServiceNow with Short description: AL21-Non-charged Device Low Battery. Battery running low -Listen to 50% of call - call ends | - interaction created as WIP | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS tested on KP101
KP88 | AL21 -Immigration - not answered | AL21 has been created - API to PD displayed in activity stream - call made to HMU -unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | IMMIGRATION DON'T GET PD CALLS tested on KP101
KP89 | AL22-Immigration - answered | AL22 has been created - API to PD displayed in activity stream - call made to HMU - interaction created in ServiceNow with Short description: AL22 Automated voice message to Device Wearer - call ends - interaction closed | - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP104 AND KP 105
KP90 | AL22-Immigration - abandoned | "AL22 has been created - API to PD displayed in activity stream - call made to HMU - interaction created in ServiceNow with Short description: AL22 Automated voice message to Device Wearer -Listen to 50% of call - call ends | - interaction created as WIP | 6 | 6 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP104 AND KP 105
KP91 | AL22-Immigration - not answered | AL22 Alert case - API to PD displayed in activity stream - call made to HMU - unsuccesful message in actiivity stream - needs attention flag updated | activity stream updated needs attention flag updated after 1 hour | 5 | 5 | Out of Scope | IMMIGRATION DON'T GET PD CALLS Tested on KP104 AND KP 105
KP92 | AL23 - Bail - answered | AL23 has been created - API to PD displayed in activity stream - call made to HMU and picked up - call ends - update investigation outcome field on case to Violation confirmed - update resolution field to completed - update state to resolved - promote to enforcement AL105 - create breach pack" | Short description: AL23 Automated voice message to Device Wearer - auto set first response date and time field in table - First Call Outcome data field populated on case - interaction updated as Closed Complete - needs attention flag updated - investigation outcome field set to Violation confirmed - resolution field set to completed - state set to resolved - interaction created on AL23 shown on AL105 breach pack" | 9 | 9 | Pass
KP93 | AL23 - Non-Bail - abandoned | "AL23 has been created - API to PD displayed in activity stream - call made to HMU - interaction created in ServiceNow with Short description: AL22 Automated voice message to Device Wearer -Listen to 50% of call-Call Abandoned - call ends investigation outcome field set to Violation confirmed - resolution field set to completed - state set to Closed Auto set first response date and time field promote to enforcement AL105 - create breach pack -run KPI 6 report" | "Short description: AL23 Automated voice message to Device Wearer interaction created on AL23 and shown on AL105 breach pack auto set first response date and time field | 13 | 13 | Pass
KP94 | AL23 - Bail - not answered | "AL23 has been created - API to PD displayed in activity stream - call made to HMU unsuccessful message in actiivity stream - needs attention flag updated auto set first response date and time field -investigation outcome field set to Violation confirmed - resolution field set to completed - state set to Closed Auto set first response date and time field wait for 15 minutes before promoting promote to enforcement AL105 - create breach pack -run KPI 6 report" | "Short description: AL23 Automated voice message to Device Wearer interaction created on AL23 and shown on AL105 breach pack auto set first response date and time field | 13 | 13 | Pass
KP95 | AL02-Immigration | - Create an AL02 | KPI6- First Call Outcome not populated | 1 | 1 | Pass | No first call outcome - Immigration
KP96 | AL04-Immigration | - Create an AL04 | KPI6- First Call Outcome not populated | 1 | 1 | Pass | No first call outcome - Immigration
KP97 | AL05-Immigration | - Create an AL05 | KPI6- First Call Outcome not populated | 1 | 1 | Pass | No first call outcome - Immigration
KP98 | AL19-Immigration | KPI6- Manual adding first respone date/time leave balnk | KPI6- Manual adding first respone date/time leave balnk | 1 | 1 | Pass
KP99 | AL20-Immigration | KPI6- Manual adding first respone date/time out of sla | KPI6- Manual adding first respone date/time out of sla | 1 | 1 | Pass
KP100 | AL23-Immigration | AL23 Alert created - no API to PD in activity stream - note in activity stream to indicate immigration no contact number available - case set to resolved KPI6-Manual Adding First respone date/time | AL23 Alert created - no API to PD in activity stream - note in activity stream to indicate immigration no contact number available - case set to resolved KPI6-Manual Adding First respone date/time | 6 | 6 | Pass
KP101 | AL22-Immigration | AL22 Alert created - no API to PD in activity stream - note in activity stream to indicate immigration no contact number available - case set to resolved KPI6-Manual Adding First respone date/time Leave date and time blank | AL22 Alert created - no API to PD in activity stream - note in activity stream to indicate immigration no contact number available - case set to resolved KPI6-Manual Adding First respone date/time Leave date and time blank | 6 | 6 | Pass
KP102 | AL19-Bail | AL19 Alert created - case set to resolved | no API generated for PD | 2 | 2 | Pass
KP103 | AL19-Non Bail | AL19 Alert created - case set to resolved | no API generated for PD | 2 | 2 | Pass

## Sheet3
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Test Data Used | Executed By | Approved By

## Sheet 4
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Test Data Used | Executed By | Approved By

## Validation (hidden)
Pass
Fail
No Run
Not Completed
In Progress
Out of Scope
Development
Blocked
Not Started

## Defects
Incident / JIRA ref | Test ID | Issue | Description | Category | Impact Rating (H-M-L) | Date Opened | Date Resolved | Target Release Date | Status | Post Production Check Y/N | Resolution | Release | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
6.1.25
Note on J1: Barlow, Beverley (UK & Europe): Open, Fixed, Retest, Training, Closed

## Sheet1 (hidden)
Testing Timeline
| 19th |  | 20th |  | 21st | 24th | 25th | 26th | 27th | 28th
ST | OE44 * Install alcohol kit | ST | DV50 * Asset Manager BPSS persona | ST | DV50 * Asset Manager BPSS persona
KW | DV41 * Field Service Officer persona | ST | DV51 * Asset Manager CTC persona | ST | DV51 * Asset Manager CTC persona
KW | DV42 * Field Service Officer SPECIALS persona | ST | DV21 * Field Service Scheduler BPSS persona | ST | DV21 * Field Service Scheduler BPSS persona
LJ | DV44 * Quality Assurance CTC persona | ST | DV22 * Field Service Scheduler CTC persona | ST | DV22 * Field Service Scheduler CTC persona
EM | DV48 * CMT Immigration persona FAILED | TL / MHI | TA08 * atv breaches |  | TA31
EM | DV49 * CMT (MoJ) personas PASSED | ST | OEO7 * install following OE01 decom |  | TA10 / OE70
ST | OE69 * install NFD | EM | TA04 *EXCLUSION | EM | TA04 *EXCLUSION
EM | TA09 / OE69 * start the AL18 process | EM | TA30 *AL15 | EM | TA30 *AL15
TL / MHI | TA01 / OE01 * finish generating the atvs & breach packs | EM | TA47 * AL24 -SPOOF | EM | TA47 * AL24 -SPOOF
TL / MHI | TA52 / OE01 * generate AL04 | LJ | TA48 * AL20 |  | OE06
ST | TA43 / OE01 * request spoof event from AUEM | LJ | OE04 * check further visit has generated after previous visit booked off as faulty equipment |  | OE76
ST | OE01 * decom kit once event has been spoofed | ST | OE01 * decom kit |  | OE08
EM / ST & KW | OE04 * Create order * Assign WOT to Mark * 2x no show visits | ST | OE03 * 2x no show |  | TA41
ST & KW | OE03 * Assign WOT to Mark * 2x no show visits | TL / MHI | TA02 * 2x no show breach |  | OE09 | NO SHOW
TL / MHI | TA05 / OE02 * Create multiple exclusions Day 1 | TL / MHI | TA05 / OE02 * Create multiple exclusions Day 2 |  | OE10 | BOOK OFFS
TL / MHI & ST | TA11 / OE02 * Generate strap tamper * Complete tamper visit | TL / MHI | TA46 * breach |  | OE15
TL / MHI | TA33 / OE20 * battery dead | ST | TA03 * 2x no show |  | OE16
MS | OE08 * Create order | TL / MHI | TA03 * breach |  | OE17
MS | OE09 * Create order | ST | OE11 * 2x no show |  | OE12
MS | OE10 * Create order | TL / MHI | TA13 * breach |  | OE13
MS | OE11 * Create order | LJ | TA68 * breach | LJ | TA68 * breach
MS | OE12 * Create order | EM | OE18 * decom
MS | OE13 * Create order | MS | OE15 * create order
CL | OE45 * Create order | MS | OE16 * create order
CL | OE46 * Create order | MS | OE17 * create order
CL | OE47 * Create order | MS | OE19 * create order
ST | OE14 * decom kit | MS | OE21 * create order
ST | OE20 * install kit | MS | OE22 * create order
TL / MHI | TA08 * start atv breaches | MS | OE23 * create order
|  | MS | OE24 * create order
|  | MS | OE25 * create order
|  | MS | OE26 * create order | MS | OE26 * create order
|  | MS | OE27 * create order
|  | MS | OE28 * create order | MS | OE28 * create order
|  | CL | OE29 * create order | MS | OE29 * create order
|  | CL | OE30 * create order | MS | OE30 * create order
|  | CL | OE31 * create order | MS | OE31 * create order
|  | CL | AC01 * create order | CL | AC01 * create order
|  | CL | AC02 * create order | CL | AC02 * create order
|  | CL | AC03 * create order | CL | AC03 * create order
|  | CL | AC04 * create order | CL | AC04 * create order
|  | LJ | DV41 * Field Service Officer persona
|  | LJ | DV42 * Field Service Officer SPECIALS persona
|  | LJ | TA40 * once the 2x no shows are complete - create a new installation work order
|  | ST | TA40 * threatening words & behaviour
|  | LJ | TA40 * breach
|  | TL / MHI | TA58 * aggregation
|  | TL / MHI | TA59 * aggregation
|  | TL / MHI | TA60 * aggregation |  | TA60 * aggregation
|  | TL / MHI | TA61 * aggregation |  | TA61 * aggregation
|  | TL / MHI | TA62 * aggregation |  | TA62 * aggregation
|  | ST | TA46 * 1x threatening words & behaviour
|  | EM | TA46 * breach
|  | LJ | OE49
|  | LJ | OE50

## OVERALL
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Issue/Defect | SERCO JIRA ID | SNOW defect ID | Approved By
0