## Version Control
Document Information
Title | Test Execution Log
Title | March Release
Release Identifier | RLSE0010182, RLSE0010184
Author | Beverley Barlow
Document Version History
Version | Date | Summary of Changes
0.1 | 2026-02-03 | Draft RLSE0010182
0.2 | 2026-02-05 | Working Copy - RLSE0010184 added
Test Evidence Repository
Test Execution Evidence is stored at this link |  | Link to Test Evidence Repository
Scope of Release
This release implements a Servicenow upgrade
Defect/Story ID | Type | Details
STRY0084121 | Enhancement | [CEMO] - AC Eligible Offence Type sent in from CEMO
STRY0084135 | Enhancement | [CEMO] New DAPO Order Clause Number as a committed offence
STRY0084158 | Enhancement | CEMO - Ability to send multiple offences and offence dates
STRY0084107 | Enhancement | [CEMO] MAPPA Category field on the Device Wearer profile
STRY0089883 | Enhancement | [CEMO] CEPR field to be mapped
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement
Enhancement

## Summary
|  |  | Phase 6 DASHBOARD |  |  |  | SHEET4 DASHBOARD |  |  |  | OVERALL DASHBOARD
Execution Progress |  |  |  | Execution Progress |  |  |  | Execution Progress
Steps Completed | 0 |  |  | Steps Completed | 0 |  |  | Steps Completed | 0
Steps Remaining | 142 |  |  | Steps Remaining | 93 |  |  | Steps Remaining | 0
Total Steps | 142 |  |  | Total Steps | 93 |  |  | Total Steps | 0
% Complete | 0% |  |  | % Complete | 0% |  |  | % Complete | #DIV/0!
Script Status |  |  |  | Script Status |  |  |  | Script Status
Pass | 0 | 0% |  | Pass | 0 | 0% |  | Pass | 0 | #DIV/0!
Fail | 0 | 0% |  | Fail | 0 | 0% |  | Fail | 0 | #DIV/0!
No Run | 0 | 0% |  | No Run | 0 | 0% |  | No Run | 0 | #DIV/0!
Not Completed | 0 | 0% |  | Not Completed | 0 | 0% |  | Not Completed | 0 | #DIV/0!
In Progress | 0 | 0% |  | In Progress | 0 | 0% |  | In Progress | 0 | #DIV/0!
Out of Scope | 0 | 0% |  | Out of Scope | 0 | 0% |  | Out of Scope | 0 | #DIV/0!
Not Started | 14 | 100% |  | Not Started | 18 | 100% |  | Not Started | 0 | #DIV/0!
TOTAL | 14 |  |  | TOTAL | 18 |  |  | TOTAL | 0
|  |  | Acquisitive Crime DASHBOARD |  |  | Phase 7 DASHBOARD
Execution Progress |  |  |  | Execution Progress
Steps Completed | 0 |  |  | Steps Completed | 0
Steps Remaining | 9 |  |  | Steps Remaining | 88
Total Steps | 9 |  |  | Total Steps | 88
% Complete | 0% |  |  | % Complete | 0%
Script Status |  |  |  | Script Status
Pass | 0 | 0% |  | Pass | 0 | 0%
Fail | 0 | 0% |  | Fail | 0 | 0%
No Run | 0 | 0% |  | No Run | 0 | 0%
Not Completed | 0 | 0% |  | Not Completed | 0 | 0%
In Progress | 0 | 0% |  | In Progress | 0 | 0%
Out of Scope | 0 | 0% |  | Out of Scope | 0 | 0%
Not Started | 1 | 100% |  | Not Started | 7 | 100%
TOTAL | 1 |  |  | TOTAL | 7

## Phase 6
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Data notes | Tested by | Story
CEMO601 | New Order/ Adult / DAPO / Curfew and Exclusion / Single offence | 1. CEMO EMS Case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10. install | - cemo new order API received - interaction, case, mon order, work order and work order task created - DAPO Order Clause Number populated on committed offence | 10 |  | Not Started | Test - STRY0084135 [CEMO] New DAPO Order Clause Number as a committed offence. Testing only one offence |  |  | STRY0084135
CEMO602 | New Order/ Adult / DAPO / Curfew only / Multiple offences | 1. CEMO EMS Case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created - multiple offences with and without dates populated on CEMO Mon Order | 9 |  | Not Started | Test - STRY0084158 CEMO - Ability to send multiple offences and offence dates |  |  | STRY0084158
CEMO603 | CEMO/Adult/New Order/Verified address/GPS Dapol RF & Exclusion/Inclusion & trail | 1. CEMO EMS Case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 |  | Not Started | 3 addresses. all disabilities. all risk. multiple exclusion zones. have ez to end before order end date |  |  | Regression test
CEMO604 | CEMO/Adult/New Order/GPS DAPOL Parole/ Trail only | 1. CEMO EMS Case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 |  | Not Started | Missed in error checkbox checked - sent in by probation |  |  | Regression test
CEMO605 | CEMO/Adult/New Order/IAS/RF/HDC | 1. CEMO EMS Case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10. Install at Source WOT closed complete 11. 2nd WOT to Installation Location generates 12. Install at Installation location | - cemo new order API received - interaction, case, mon order, work order and work order task created | 12 |  | Not Started | IAS with installation location. WOT generates for installation location when WOT at IAS closed completed |  |  | STRY0089352 RLSE0010214
CEMO606 | CEMO/Adult/New Order/EDS GPS Trail with AM | 1. CEMO EMS Case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10.Create EMS for AM 11. Create MON, monreq and moncon 12. Create WO/WOT 13. Incomplete visit at prison 14. 2nd WOT generated to address 15. Install | - cemo new order API received - interaction, case, mon order, work order and work order task created | 15 |  | Not Started | IAS with no installation location - unsuccessful visit at prison. 2nd wot generate from devwr addresses Abstinence |  |  | STRY0089352 RLSE0010214
CEMO607 | CEMO/Adult/New Order/SDS AM only/ TAS probation office/ NFA | 1. CEMO EMS Case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 |  | Not Started | TAS at probation AM monitoring |  |  | Regression test
CEMO608 | CEMO/Child/New Order/Verified address/DTO ISSP/ Trail and exclusion | 1. CEMO EMS Case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 |  | Not Started | from YCS |  |  | Regression test
CEMO609 | CEMO/Child/New Order/Verified address/HDC (Section 91)/RF, Exclusion/Inclusion & Trail | 1. CEMO comes in 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - interaction, case, mon order, work order and work order task created | 9 |  | Not Started | from Feltham YOI, all disabilities, all risks |  |  | Regression test
CEMO610 | CEMO/Adult/New Order/Verified address/ GPS determinate Sentence -add em (EMLV)/ Curfew, GPS trail and AM | 1. CEMO comes in 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10. Create manual AM EMS case 11. Create MON, MONREQ and MONCON 12. Create WO and WOT | - Cemo new order api received - Case, mon, wo and wot created | 12 |  | Not Started | from probation |  |  | Regression test
CEMO611 | CEMO/Adult/New Order/New Order/Verified Address/IPP(GPS Parole)/ GPS trail | 1. CEMO comes in 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - Cemo new order api received - Case, mon, wo and wot created | 9 |  | Not Started | from probation |  |  | Regression test
CEMO612 | CEMO/DAPO (existing profile from CEMO601) / curfew | 1. CEMO comes in 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - Cemo new order api received - Case, mon, wo and wot created | 9 |  | Not Started | to check existing device wearer. Do once CEMO601 has been ended due to CEMOVAR01 |  |  | Regression test
CEMO613 | CEMO/Adult/ New Order/ Verified Address/IAS/GPS HDC curfew and trail | 1. CEMO comes in 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10. WOT at IAS closed incomplete 11. 2nd WOT generates for installation location 12. Install at installation location | - Cemo new order api received - Case, mon, wo and wot created -Upon WOT at IAS closed incomplete, 2nd WOT generates for installation locaton | 12 |  | Not Started | IAS WOT closed incomplete. 2nd wot generates for installation location |  |  | RLSE0010214 - STRY0089352
CEMO614 | CEMO/Adult/New Order/EDS AM only/ TAS probation office/ NFA | 1. CEMO EMS Case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10.Closed incomplete WOT 11. 2nd WOT with no location generates | - cemo new order API received - interaction, case, mon order, work order and work order task created - Close incomplete initial WOT and 2nd WOT with no location generates | 9 |  | Not Started | TAS at probation - closed incomplete. 2nd WOT with no location generates AM monitoring |  |  | RLSE0010214 - STRY0089352
Column1

## Phase 7
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Data notes | Tested by | Story
CEMO701 | NFD new order / NFA / TAS / Location tracking /CEPR/Mappa Cat 1 (not successful visit) | 1. CEMO EMS Case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer with Mappa Cat 1 and CEPR 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10. WOT closed incomplete 11. 2nd WOT appears with no locatoin | - cemo new order API received - case, mon order, work order and work order task created - CEMO and SNOW DEVWR profile has CEPR and MAPPA Cat 1 - 2nd WOT appears with no location | 11 |  | Not Started |  |  |  | STRY0089883 STRY0084107
CEMO702 | NFD new order / Verified address (Scottish)/ TAS / Location tracking / Mappa Cat 2 /CEPR | 1. CEMO EMS Case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer with Mappa Cat 2 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - case, mon order, work order and work order task created - CEMO and SNOW DEVWR profile has MAPPA Cat 2 | 9 |  | Not Started |  |  |  | STRY0084107 STRY0089883
CEMO703 | SOLO new order / Verified address (NI) / Location tracking and exclusion zone / Mappa Cat 3 | 1. CEMO EMS Case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer with Mappa Cat 3 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task | - cemo new order API received - case, mon order, work order and work order task created - CEMO and SNOW DEVWR profile has MAPPA Cat 3 | 9 |  | Not Started |  |  |  | STRY0084107
CEMO704 | SOLO new order / Verified address (liverpool)/ location tracking/ install and curfew/ preexisting CTC device wearer | 1.Find/Create CTC device wearer 2. CEMO EMS Case gets created 3. check cemo device wearer and mon order forms 4. update with existing Device Wearer 5. update Case 6. update Monitoring Order 7. check Monitoring Requirements 8. check Monitoring Configuration 9. update Work Order 10. update Work Order Task | - cemo new order API received - case, mon order, work order and work order task created - CEMO recognises existing device wearer. - Agent can use existing device wearer | 10 |  | Not Started |  |  |  | Regression
CeMO705 | Preexisting non-ctc (prison then HO) | 1. CEMO EMS case from prison gets created 2. check CEMO devwr and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10.CEMO EMS case from HO gets created 11. check CEMO devwr and mon order forms 12. update devwr using devwr from prison cemo 13. Check if CEMO EMS case from prison is not viewable using BPSS 14. update Case 15. update Monitoring order 16. check monitoring requirements 17. check monitoring configuration 18. update WO 19. update WOT | -able to see existing device wearer from HO playbook -use existing devwr for the HO order -Agent proceeds as normal -BPSS agent won't able to see order and profile once HO order is attached | 19 |  | Not Started |  |  |  | Regression
CEMO706 | NFD new order / liverpool / TAS / Location tracking /CEPR/Mappa Cat 1 (Closed complete) 2nd wot not appearing | 1. CEMO EMS case gets created 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10. Install successfully at IAS (Closed complete) 11. No 2nd WOT | - cemo new order API received - interaction, case, mon order, work order and work order task created - AC offences without dates populated on CEMO Mon Order -No 2nd WOT after closed complete IAS WOT | 11 |  | Not Started |  |  |  | RLSE0010214 - STRY0089352
CEMO707 | HO order comes in and processed and then prison order comes in | 1. CEMO EMS case from HO gets created 2. check CEMO devwr and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10.CEMO EMS case from prison gets created 11. check CEMO devwr and mon order forms 12. CEMO devwr and MO forms are still viewable 13. System will identify a match but details will not be shown to BPSS 14. update Case 15. update Monitoring order 16. check monitoring requirements 17. check monitoring configuration 18. update WO 19. update WOT | BPSS agent will be able to see prison order but not see details of device wearer match CTC agent will be able to see details of the match, proceed with the order. Once the EMS case is attached to the CTC devwr then CEMO case will no longer be visible to BPSS | 19 |  | Not Started |  |  |  | Regression

## Acquisitive Crime
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Data notes | Tested by | Story
CEMOAC01 | Adult / Verified Address/ Post-release/ AC Parole / IAS pilot prison / Trail only | 1. CEMO case comes in with offence 2. check cemo device wearer and mon order forms 3. update Device Wearer 4. update Case 5. update Monitoring Order 6. check Monitoring Requirements 7. check Monitoring Configuration 8. update Work Order 9. update Work Order Task 10. Install successfully at IAS (Closed complete) 11. No 2nd WOT | - cemo new order API received - interaction, case, mon order, work order and work order task created - AC offences without dates populated on CEMO Mon Order -No 2nd WOT after closed complete IAS WOT | 9 |  | Not Started | test STRY0084121 - [CEMO] - AC Eligible Offence Type sent in from CEMO IAS with no installation location -succcessful and no 2nd WOT | CEMO MoJ advised will not be sending offence dates for AC offences |  | STRY0084121 STRY0089352/RLSE0010214

## Variations
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Data notes | Tested by | Story
CEMOVAR01 | SR11 (bail end) for CEMO601 | 1. SR11 comes in from cemo API 2. Check details on EMS case 3. update case 4. update MON 5. Create WO 6. Create WOT 7. Decom equipment | -cemo SR11 update api received -SR11 case created -enough info on SR11 | 7 |  | Not Started |  |  |  | Regression
CEMOVAR02 | SR11 (bail end) for immigration | 1. SR11 comes in from cemo API 2. Check details on EMS case 3. update case 4. update MON 5. Create WO 6. Create WOT 7. Decom equipment | -cemo SR11 update api received -SR11 case created -enough info on SR11 | 7 |  | Not Started |  |  |  | Regression
CEMOVAR03 | Interim variation AV SR04 for manual order | 1. Manually create interaction for HDC order curfew/GPS/ AM 2.Create EMS case 3.Create Mon,moncon, monreq 4. Create WO and WOT 5. Install 6. CEMO for SR04 comes in 7. Check cemo devwr and mon order forms 8. Update DEVWR 9. Update Case 10. Add moncon 11. Create WO and WOT 12. Install | - cemo SR04 update APi received - SR04 ems case created - Enough info on ems case that gets created | 12 |  | Not Started | AV SR04 |  |  | Regression
CEMOVAR04 | SR04 AV for CEMOAC01 | 1. CEMO for SR04 comes in 2.check cemo devwr and mon order forms 3. update DEVWR 4.update case | - cemo SR04 update APi received - SR04 ems case created - Enough info on ems case that gets created | 4 |  | Not Started | AV SR04 - No visit required |  |  | Regression
CEMOVAR05 | SR05 AV 2nd address for CEMO609 | 1. CEMO for SR05 comes in 2.check cemo devwr and mon order forms 3. update DEVWR 4.update case 5. add moncon 6. Create WO 7. Create WOT 8. Install | - cemo SR05 update APi received - SR05 ems case created - Enough info on ems case that gets created | 8 |  | Not Started | AV SR05 2nd address |  |  | Regression
CEMOVAR06 | SR08 Garden Access (other) CEMO609 | 1. CEMO for SR08 Other comes in 2. check cemo devwr and mon order forms 3. update devwr 4. update case 5. Create WO 6. Create WOT. | - cemo SR08 update APi received - SR08 ems case created - Enough info on ems case that gets created | 6 |  | Not Started |  |  |  | Regression
CEMOVAR07 | SR08 Admin Error CEMO609 | 1. CEMO for SR08 Other comes in 2. check cemo devwr and mon order forms 3. update devwr 4. update case | - cemo SR08 update APi received - SR08 ems case created - Enough info on ems case that gets created | 4 |  | Not Started | no visit required |  |  | Regression
CEMOVAR08 | SR08 Add EZ on CEMO602 | 1. CEMO for SR08 Add EZ 2. check cemo devwr and mon order forms 3. update devwr 4. update case 5. Create WO 6. Create WOT. | - cemo SR08 update APi received - SR08 ems case created - Enough info on ems case that gets created | 6 |  | Not Started |  |  |  | Regression
CEMOVAR09 | SR21 CEMO607 | 1. CEMO for SR21 comes in 2. check cemo devwr and mon order forms 3. Update case 4. Run playbook 5. Amend Mon order 6. Create WO and WOT | - cemo SR21 update APi received - SR21 ems case created - Enough info on ems case that gets created | 6 |  | Not Started |  |  |  | Regression
CEMOVAR10 | SR08 Change to device type CEMO702 (Imm) | 1. CEMO for SR08 Change to Device type 2. check cemo devwr and mon order forms 3. update devwr 4. update case 5. Create WO 6. Create WOT. 7. Equipment swap to NFD | - cemo SR08 update APi received - SR08 ems case created - Enough info on ems case that gets created | 7 |  | Not Started |  |  |  | Regression
CEMOVAR11 | Variation for IMM orders that are not on CEMO (AV) | 1. Manually create interaction for Imm order 2.Create EMS case 3.Create Mon,moncon, monreq 4. Create WO and WOT 5. Install 6. CEMO for SR04 comes in 7. Check cemo devwr and mon order forms 8. Update DEVWR 9. Update Case | - cemo SR04 update APi received - SR04 ems case created - Enough info on ems case that gets created | 12 |  | Not Started |  |  |  | Regression
CEMOVAR12 | SR08 Change to curfew hours | 1. CEMO for SR08 comes in 2. check OVT on EMS case | order variation type displays on ems case | 2 |  | Not Started |  |  |  | Regression
CEMOVAR13 | SR08 Change to address (immigration) | 1. CEMO for SR08 comes in 2. check OVT on EMS case | order variation type displays on ems case | 2 |  | Not Started |  |  |  | Regression
CEMOVAR14 | SR08 Change to an existing Inclusion or Exclusion Zone(s) | 1. CEMO for SR08 comes in 2. check OVT on EMS case | order variation type displays on ems case | 2 |  | Not Started |  |  |  | Regression
CEMOVAR15 | SR08 Order suspension | 1. CEMO for SR08 comes in 2. check OVT on EMS case | order variation type displays on ems case | 2 |  | Not Started |  |  |  | Regression
CEMOVAR16 | SR08 Change to Personal Details (immigration) | 1. CEMO for SR08 comes in 2. check OVT on EMS case | order variation type displays on ems case | 2 |  | Not Started |  |  |  | Regression
CEMOVAR17 | SR08 Change to Enforceable conditions | 1. CEMO for SR08 comes in 2. check OVT on EMS case | order variation type displays on ems case | 2 |  | Not Started |  |  |  | Regression
CEMOVAR18 | SR08 Other (immigration) | 1. CEMO for SR08 comes in 2. check OVT on EMS case | order variation type displays on ems case | 2 |  | Not Started |  |  |  | Regression

## Validation (hidden)
Pass | Open
Fail | Retest
No Run | Ready for Prod
Not Completed | Training
In Progress | Closed
Out of Scope | On Hold
Development
Blocked
Not Started

## Defects
Incident / JIRA ref | Test ID | Issue | Description | Category | Impact Rating (H-M-L) | Date Opened | Date Resolved | Target Release Date | Status | Resolution | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
6.1.25
Note on J1: Barlow, Beverley: Open - Draft, WIP Retest - BAT testing Ready for Prod - retest passed Training - workaround or info for training Closed - test data or raised in error On Hold - in future release

## Sheet1 (hidden)
Testing Timeline
| 19th |  | 20th |  | 21st | 24th | 25th | 26th | 27th | 28th
ST | OE44 * Install alcohol kit | ST | DV50 * Asset Manager BPSS persona | ST | DV50 * Asset Manager BPSS persona
KW | DV41 * Field Service Officer persona | ST | DV51 * Asset Manager CTC persona | ST | DV51 * Asset Manager CTC persona
KW | DV42 * Field Service Officer SPECIALS persona | ST | DV21 * Field Service Scheduler BPSS persona | ST | DV21 * Field Service Scheduler BPSS persona
LJ | DV44 * Quality Assurance CTC persona | ST | DV22 * Field Service Scheduler CTC persona | ST | DV22 * Field Service Scheduler CTC persona
EM | DV48 * CMT Immigration persona FAILED | TL / MHI | TA08 * atv breaches |  | TA31
EM | DV49 * CMT (MoJ) personas PASSED | ST | OEO7 * install following OE01 decom |  | TA10 / OE70
ST | OE69 * install NFD | EM | TA04 *EXCLUSION | EM | TA04 *EXCLUSION
EM | TA09 / OE69 * start the AL18 process | EM | TA30 *AL15 | EM | TA30 *AL15
TL / MHI | TA01 / OE01 * finish generating the atvs & breach packs | EM | TA47 * AL24 -SPOOF | EM | TA47 * AL24 -SPOOF
TL / MHI | TA52 / OE01 * generate AL04 | LJ | TA48 * AL20 |  | OE06
ST | TA43 / OE01 * request spoof event from AUEM | LJ | OE04 * check further visit has generated after previous visit booked off as faulty equipment |  | OE76
ST | OE01 * decom kit once event has been spoofed | ST | OE01 * decom kit |  | OE08
EM / ST & KW | OE04 * Create order * Assign WOT to Mark * 2x no show visits | ST | OE03 * 2x no show |  | TA41
ST & KW | OE03 * Assign WOT to Mark * 2x no show visits | TL / MHI | TA02 * 2x no show breach |  | OE09 | NO SHOW
TL / MHI | TA05 / OE02 * Create multiple exclusions Day 1 | TL / MHI | TA05 / OE02 * Create multiple exclusions Day 2 |  | OE10 | BOOK OFFS
TL / MHI & ST | TA11 / OE02 * Generate strap tamper * Complete tamper visit | TL / MHI | TA46 * breach |  | OE15
TL / MHI | TA33 / OE20 * battery dead | ST | TA03 * 2x no show |  | OE16
MS | OE08 * Create order | TL / MHI | TA03 * breach |  | OE17
MS | OE09 * Create order | ST | OE11 * 2x no show |  | OE12
MS | OE10 * Create order | TL / MHI | TA13 * breach |  | OE13
MS | OE11 * Create order | LJ | TA68 * breach | LJ | TA68 * breach
MS | OE12 * Create order | EM | OE18 * decom
MS | OE13 * Create order | MS | OE15 * create order
CL | OE45 * Create order | MS | OE16 * create order
CL | OE46 * Create order | MS | OE17 * create order
CL | OE47 * Create order | MS | OE19 * create order
ST | OE14 * decom kit | MS | OE21 * create order
ST | OE20 * install kit | MS | OE22 * create order
TL / MHI | TA08 * start atv breaches | MS | OE23 * create order
|  | MS | OE24 * create order
|  | MS | OE25 * create order
|  | MS | OE26 * create order | MS | OE26 * create order
|  | MS | OE27 * create order
|  | MS | OE28 * create order | MS | OE28 * create order
|  | CL | OE29 * create order | MS | OE29 * create order
|  | CL | OE30 * create order | MS | OE30 * create order
|  | CL | OE31 * create order | MS | OE31 * create order
|  | CL | AC01 * create order | CL | AC01 * create order
|  | CL | AC02 * create order | CL | AC02 * create order
|  | CL | AC03 * create order | CL | AC03 * create order
|  | CL | AC04 * create order | CL | AC04 * create order
|  | LJ | DV41 * Field Service Officer persona
|  | LJ | DV42 * Field Service Officer SPECIALS persona
|  | LJ | TA40 * once the 2x no shows are complete - create a new installation work order
|  | ST | TA40 * threatening words & behaviour
|  | LJ | TA40 * breach
|  | TL / MHI | TA58 * aggregation
|  | TL / MHI | TA59 * aggregation
|  | TL / MHI | TA60 * aggregation |  | TA60 * aggregation
|  | TL / MHI | TA61 * aggregation |  | TA61 * aggregation
|  | TL / MHI | TA62 * aggregation |  | TA62 * aggregation
|  | ST | TA46 * 1x threatening words & behaviour
|  | EM | TA46 * breach
|  | LJ | OE49
|  | LJ | OE50

## OVERALL
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Data notes | Tested by | Story
0