## Version Control
Document Information
Title | Test Execution Log
Title | March Release
Release Identifier
Author | David Allan
Document Version History
Version | Date | Summary of Changes
0.1 | 2026-02-13 | Initial Issue
0.2
Test Evidence Repository
Test Execution Evidence is stored at this link |  | Link to Test Evidence Repository
Scope of Release
This release implements a Servicenow upgrade - addressing KPI enhancements not part of BAT Testing
Defect/Story ID | Type | Details
STRY0070709 | Enhancement | KPI 1&2&6&9&10&11 - Include Curfew hours in report & list view
STRY0071939 | Enhancement | PASS/FAIL Calculation for KPI 6 amended for AL04, AL23 alerts
STRY0083447 | Enhancement | KPI 6 Head Due date calculation to include schedules
STRY0086767 | Enhancement | KPI 4 & 5 - to look at Escalated From case
STRY0086774 | Enhancement | KPI 3 to not show WOTs where no notification is required
STRY0086775 | Enhancement | KPI 11 - Notification received date and time as a column in the report
STRY0086776 | Enhancement | Filter KPI 1 & 2 to only show WOTs from an SR01 / 02 cases
STRY0086885 | Enhancement | New column on the KPI 6a&b report
STRY0086886 | Enhancement | New Column on the KPI 6a report
STRY0086888 | Enhancement | KPI 8 Column additions
STRY0088343 | Enhancement | KPI 1 Pass / Fail calculation to include schedules
STRY0088344 | Enhancement | KPI 2 Pass / Fail calculation to include schedules
STRY0088347 | Enhancement | KPI 9 Pass / Fail calculation to include schedules
STRY0088348 | Enhancement | KPI 10 Pass / Fail calculation to include schedules
STRY0088352 | Enhancement | KPI 6 Pass / Fail calculation to include schedules
STRY0088541 | Enhancement | New dashboard in the KPI 6 report - 6d
STRY0088542 | Enhancement | New dashboard in the KPI 6 report - 6e
STRY0088559 | Enhancement | KPI 6 dashboard filter update
STRY0088799 | Enhancement | Ability to determine if a date & time was within Blackout &/ or personalised schedule

## Summary
Phase 6 DASHBOARD
Execution Progress
Steps Completed | 0
Steps Remaining | 137
Total Steps | 137
% Complete | 0%
Script Status
Pass | 0 | 0%
Fail | 0 | 0%
No Run | 0 | 0%
Not Completed | 0 | 0%
In Progress | 0 | 0%
Out of Scope | 0 | 0%
Not Started | 80 | 100%
TOTAL | 80

## KPI TEAM
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Data notes | Tested by | Story
KPSE01 | KPI 1 new column on report and list view | No data set up required - verify that all KPI data has been cloned from Training DB w/c 16th Feb Open the KPI Dashboard View the KPI 1 report Verify that the report contains a new column called 'Schedule hours' Open the KPI 1 List View Verify that the view contains a new column called 'Schedule hours' | Schedule Hours will appear on report and list view | 5 |  | Not Started |  |  |  | STRY0070709
KPSE02 | KPI 2 new column on report and list view | No data set up required - verify that all KPI data has been cloned from Training DB w/c 16th Feb Open the KPI Dashboard View the KPI 2 report Verify that the report contains a new column called 'Schedule hours' Open the KPI 2 List View Verify that the view contains a new column called 'Schedule hours' | Schedule Hours will appear on report and list view | 5 |  | Not Started |  |  |  | STRY0070709
KPSE03 | KPI 6 new column on report and list view | No data set up required - verify that all KPI data has been cloned from Training DB w/c 16th Feb Open the KPI Dashboard View the KPI 6 report Verify that the report contains a new column called 'Schedule hours' Open the KPI 6 List View Verify that the view contains a new column called 'Schedule hours' Verify that Black out schedules will also be bought into this column (Scheduled hours from the WOT) | Schedule Hours will appear on report and list view Black out schedules will also be bought into this column (Scheduled hours from the WOT) | 5 |  | Not Started |  |  |  | STRY0070709
KPSE04 | KPI 9 new column on report and list view | No data set up required - verify that all KPI data has been cloned from Training DB w/c 16th Feb Open the KPI Dashboard View the KPI 6 report Verify that the report contains a new column called 'Schedule hours' Open the KPI 9 List View Verify that the view contains a new column called 'Schedule hours' | Schedule Hours will appear on report and list view | 5 |  | Not Started |  |  |  | STRY0070709
KPSE05 | KPI 10 new column on report and list view | No data set up required - verify that all KPI data has been cloned from Training DB w/c 16th Feb Open the KPI Dashboard View the KPI 10 report Verify that the report contains a new column called 'Schedule hours' Open the KPI 10 List View Verify that the view contains a new column called 'Schedule hours' | Schedule Hours will appear on report and list view | 5 |  | Not Started |  |  |  | STRY0070709
KPSE06 | KPI 11 new column on report and list view | No data set up required - verify that all KPI data has been cloned from Training DB w/c 16th Feb Open the KPI Dashboard View the KPI 11 report Verify that the report contains a new column called 'Schedule hours' Open the KPI 11 List View Verify that the view contains a new column called 'Schedule hours' | Schedule Hours will appear on report and list view | 5 |  | Not Started |  |  |  | STRY0070709
KPSE07 | KPI 6 Calculation - AL04 | Calculated on Case resolution Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When KPI 6 Call made, Interaction created & THEN power restored before 8 hours KPI Head PASS, | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE08 | KPI 6 Calculation - AL04 | Calculated on Case resolution Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When KPI 6 Call made, Interaction created & THEN power restored past 8 hours KPI Head FAIL | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE09 | KPI 6 Calculation - AL04 | Calculated on Case resolution Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When KPI 6 Call made, Interaction created & THEN power restored before 3 Days at 23:59:59, KPI Tail PASS (If head is passed, auto PASS tails) | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE10 | KPI 6 Calculation - AL04 | Interaction Created AFTER the Power restore event then KPI = VOID Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When KPI 6 Call made, NO Interaction created & power restored before 8 hours, KPI Head VOID | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE11 | KPI 6 Calculation - AL04 | Interaction Created AFTER the Power restore event then KPI = VOID Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When KPI 6 Call made, NO Interaction created & power restored before 3 Days Tail VOID (If before 8 hours) | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE12 | KPI 6 Calculation - AL04 | Calculated on Non-Compliance Enforcement created Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When KPI 6 Call made, NO Interaction created & power restored before 3 Days Tail PASS (if after 8 hours) | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE13 | KPI 6 Calculation - AL04 | alculated on Non-Compliance Enforcement created Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When KPI 6 Call made, Interaction Created & power off and case NOT promoted to enforcement after 8 hours from case creation, KPI Head FAIL | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE14 | KPI 6 Calculation - AL04 | Calculated on Non-Compliance Enforcement created Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When KPI 6 Call made, Interaction Created & power off and case NOT promoted to enforcement after 3 Days at 23:59:59 from case creation, KPI Tail FAIL | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE15 | KPI 6 Calculation - AL04 | Calculated on Non-Compliance Enforcement created Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When KPI 6 Call made, Interaction created & power still off, case promoted to enforcement (Non-Compliance Enforcement, escalated from the current Violation investigation) before 8 hours = KPI Head PASS | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE16 | KPI 6 Calculation - AL04 | Calculated on Non-Compliance Enforcement created (only AL04) Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When KPI 6 Call made, Interaction created & power still off, case promoted to enforcement (Non-Compliance Enforcement, escalated from the current Violation investigation), past 8 hours KPI head fail | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE17 | KPI 6 Calculation - AL04 | Calculated on Non-Compliance Enforcement created (only AL04) Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When KPI 6 Call made, Interaction created & power still off, case promoted to enforcement before 3 Days at 23:59:59 KPI Tail PASS | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE18 | KPI 6 Calculation - AL04 | Calculated on Non-Compliance Enforcement created (only AL04) Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When NO KPI 6 Call made, power restored before 8 hours from Case creation = KPI VOID | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE19 | KPI 6 Calculation - AL04 | Calculated on MDSS event type 9 - Power restored Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When NO KPI 6 Call made, & power not restored after 3 days at 23:59:59 from Case creation = KPI Tail FAIL | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE20 | KPI 6 Calculation - AL04 | Calculated on MDSS event type 9 - Power restored Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL04 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. When NO KPI 6 Call made, & power not restored after 8 hours from Case creation = KPI Head FAIL | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE21 | KPI 6 Calculation - AL23 | Calculated on Case resolution Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL23 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. Interaction Created and case not promoted to enforcement = KPI Head FAIL & KPI Tail FAIL | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE22 | KPI 6 Calculation - AL23 | Calculated on Case resolution Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL23 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. Interaction Created and case promoted to enforcement before 8 hours of case creation = KPI Head PASS | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE23 | KPI 6 Calculation - AL23 | Calculated on Case resolution Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL23 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. Interaction Created and case promoted to enforcement before 3 days of case creation = KPI Tail PASS | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE24 | KPI 6 Calculation - AL23 | Immigration Pre-requisite data or dependencies: - Create a new or existing Violation Investigation case with subcategory AL23 and calculated KPI 6 Head and Tail Dates Test Steps: 1. Resolve the case 2. Cases raised where the MO associated is Immigration to be automatically voided | Calculation Result as specified | 2 |  | Not Started |  |  |  | STRY0071939
KPSE25 | KPI 11 - new date column in the report | Performance Analytics Dashboard, navigate to KPI 11 report and list view Check that a new column called 'Notification Received Date and Time' is included showing the Notification Received Date and Time field on the case | New column confirmed present | 1 |  | Not Started |  |  |  | STRY0086775
KPSE26 | KPI 3 - WOTs excluded from KPI 3 report | Identify one or more WOT which have been closed successfully before the KPI 1 /2 due date, (KPI 1 / 2 PASS). Verify that these WOTs do not appear in the KPI 3 report or list view | Relevant WOTs will not appear in report | 2 |  | Not Started |  |  |  | STRY0086774
KPSE27 | KPI 1 - new filter on list view | Open the KPI 1 report or list view, Verify that the list of WOTs has an added filter to only bring in WOTs that have been generated off an SR01/SR02 case | Filter will be present and operating correctly | 2 |  | Not Started |  |  |  | STRY0086776
KPSE28 | KPI 2 - new filter on list view | Open the KPI 2 report or list view, Verify that the list of WOTs has an added filter to only bring in WOTs that have been generated off an SR01/SR02 case | Filter will be present and operating correctly | 2 |  | Not Started |  |  |  | STRY0086776
KPSE29 | KPI 6a report - new column | Navigate to the KPI 6a report Verify that new column called 'Promoted to enforcement' has been included Verify that this field contains the date and time the case was promoted to enforcement (Associated Enforcement case created on date and time) Verify this this has been added to the KPI 6 view | The column will be dispayed on the report and view | 4 |  | Not Started |  |  |  | STRY0086885
KPSE30 | KPI 6b report - new column | Navigate to the KPI 6b report Verify that new column called 'Promoted to enforcement' has been included Verify that this field contains the date and time the case was promoted to enforcement (Associated Enforcement case created on date and time) Verify this this has been added to the KPI 6 view | The column will be dispayed on the report and view | 4 |  | Not Started |  |  |  | STRY0086885
KPSE31 | KPI 6a report - new column | Navigate to the KPI 6a report Verify that a new column has been added called 'Initial onsite arrival time' , containing the date and time of the onsite arrival of the associated WOT Verify that this is also in the KPI 6 view | The column will be dispayed on the report and view | 3 |  | Not Started |  |  |  | STRY0086886
KPSE32 | KPI 8 report - new columns | Navigate to the KPI 8 report then to the raw data list Verify the presence of 2 new columns - MO Order end date (this will show the date of the Order End on the Monitoring order associated) - Resolved date and time (This will show the date and time that the Specials Investigation case was resolved) Verify that these also appear in the KPI 8 view | The column will be dispayed on the report and view | 3 |  | Not Started |  |  |  | STRY0086888
KPSE33 | KPI 1 Pass / Fail calculation to include schedules | Pre-requisite data - New device wearer created for each scenario - New monitoring order case created for DW, with new monitoring order created with a curfew requirement - A curfew schedule on the curfew mon con that is within reasonable hours to test e.g. 09:00 - 12:00 - Follow the playbooks along to the point of the WOT being created and assigned to an FMO - Close complete the WOT - Confirm the KPI 1/2 Pass SLA field on the WOT is set to Pass | KPI result as expected | 3 |  | Not Started |  |  |  | STRY0088343
KPSE34 | KPI 1 Pass / Fail calculation to include schedules | Pre-requisite data - New device wearer created for each scenario - New monitoring order case created for DW, with new monitoring order created with a curfew requirement - A curfew schedule on the curfew mon con that is within reasonable hours to test e.g. 09:00 - 12:00 - Follow the playbooks along to the point of the WOT being created and assigned to an FMO - Close incomplete the WOT inside the curfew hours of the device wearer schedule (and outside of the blackout schedule) - Confirm the KPI 1/2 Pass SLA field on the WOT is set to Pass | KPI result as expected | 3 |  | Not Started |  |  |  | STRY0088343
KPSE35 | KPI 1 Pass / Fail calculation to include schedules | Pre-requisite data - New device wearer created for each scenario - New monitoring order case created for DW, with new monitoring order created with a curfew requirement - A curfew schedule on the curfew mon con that is within reasonable hours to test e.g. 09:00 - 12:00 - Follow the playbooks along to the point of the WOT being created and assigned to an FMO - Close incomplete the WOT outside of the curfew hours of the device wearer schedule - Confirm the KPI 1/2 Pass SLA field on the WOT is set to Fail | KPI result as expected | 3 |  | Not Started |  |  |  | STRY0088343
KPSE36 | KPI 1 Pass / Fail calculation to include schedules | Pre-requisite data - New device wearer created for each scenario - New monitoring order case created for DW, with new monitoring order created with a curfew requirement - A curfew schedule on the curfew mon con that is within reasonable hours to test e.g. 09:00 - 12:00 - Follow the playbooks along to the point of the WOT being created and assigned to an FMO - Close incomplete the WOT inside of the blackout hours of the device wearer schedule - Confirm the KPI 1/2 Pass SLA field on the WOT is set to Fail | KPI result as expected | 3 |  | Not Started |  |  |  | STRY0088343
KPSE37 | KPI 2 Pass / Fail calculation to include schedules | - New CHILD device wearer created - New monitoring order case created for DW, with new monitoring order created with a curfew requirement - A curfew schedule on the curfew mon con that is within reasonable hours to test e.g. 09:00 - 12:00 - Follow the playbooks along to the point of the WOT being created and assigned to an FMO - Close complete the WOT - Confirm the KPI 1/2 Pass SLA field on the WOT is set to Pass | KPI result as expected | 6 |  | Not Started |  |  |  | STRY0088344
KPSE38 | KPI 2 Pass / Fail calculation to include schedules | - New CHILD device wearer created - New monitoring order case created for DW, with new monitoring order created with a curfew requirement - A curfew schedule on the curfew mon con that is within reasonable hours to test e.g. 09:00 - 12:00 - Follow the playbooks along to the point of the WOT being created and assigned to an FMO - Close incomplete the WOT inside the curfew hours of the device wearer schedule (and outside of the blackout schedule) - Confirm the KPI 1/2 Pass SLA field on the WOT is set to Pass | KPI result as expected | 6 |  | Not Started |  |  |  | STRY0088344
KPSE39 | KPI 2 Pass / Fail calculation to include schedules | - New CHILD device wearer created - New monitoring order case created for DW, with new monitoring order created with a curfew requirement - A curfew schedule on the curfew mon con that is within reasonable hours to test e.g. 09:00 - 12:00 - Follow the playbooks along to the point of the WOT being created and assigned to an FMO - Close incomplete the WOT outside of the curfew hours of the device wearer schedule - Confirm the KPI 1/2 Pass SLA field on the WOT is set to Fail | KPI result as expected | 6 |  | Not Started |  |  |  | STRY0088344
KPSE40 | KPI 2 Pass / Fail calculation to include schedules | - New CHILD device wearer created - New monitoring order case created for DW, with new monitoring order created with a curfew requirement - A curfew schedule on the curfew mon con that is within reasonable hours to test e.g. 09:00 - 12:00 - Follow the playbooks along to the point of the WOT being created and assigned to an FMO - Close incomplete the WOT inside of the blackout hours of the device wearer schedule - Confirm the KPI 1/2 Pass SLA field on the WOT is set to Fail | KPI result as expected | 6 |  | Not Started |  |  |  | STRY0088344
KPSE41 | KPI 9 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - a new or existing Service Request case with subcategory SR04,05,09,10 and calculated KPI 9 Due Date - a work order and work order task exist - a device wearer with existing personal schedule associated - close the WOT (complete and/or incomplete) - Where the cases is cancelled result is VOID | KPI result as expected | 5 |  | Not Started |  |  |  | STRY0088347
KPSE42 | KPI 9 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - a new or existing Service Request case with subcategory SR04,05,09,10 and calculated KPI 9 Due Date - a work order and work order task exist - a device wearer with existing personal schedule associated - close the WOT (complete and/or incomplete) - SR04,05,09,10, SR09, SR10, calculation starts = ‘Notification received date and time’ field - SR05 calculation starts – ‘When Device-Wearer will be at the additional address’ field on SR05 case - FIRST WOT ONLY On site arrival time before or on due date and before Due date time = PASS | KPI result as expected | 9 |  | Not Started |  |  |  | STRY0088347
KPSE43 | KPI 9 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - a new or existing Service Request case with subcategory SR04,05,09,10 and calculated KPI 9 Due Date - a work order and work order task exist - a device wearer with existing personal schedule associated - close the WOT (complete and/or incomplete) - SR04,05,09,10, SR09, SR10, calculation starts = ‘Notification received date and time’ field - SR05 calculation starts – ‘When Device-Wearer will be at the additional address’ field on SR05 case - FIRST WOT ONLY Onsite arrival time after due date = FAIL | KPI result as expected | 9 |  | Not Started |  |  |  | STRY0088347
KPSE44 | KPI 9 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - a new or existing Service Request case with subcategory SR04,05,09,10 and calculated KPI 9 Due Date - a work order and work order task exist - a device wearer with existing personal schedule associated - close the WOT (complete and/or incomplete) - SR04,05,09,10, SR09, SR10, calculation starts = ‘Notification received date and time’ field - SR05 calculation starts – ‘When Device-Wearer will be at the additional address’ field on SR05 case - when a visit is closed incomplete with on site arrival within curfew hours and outside black out schedule before Due date = Pass | KPI result as expected | 9 |  | Not Started |  |  |  | STRY0088347
KPSE45 | KPI 9 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - a new or existing Service Request case with subcategory SR04,05,09,10 and calculated KPI 9 Due Date - a work order and work order task exist - a device wearer with existing personal schedule associated - close the WOT (complete and/or incomplete) - SR04,05,09,10, SR09, SR10, calculation starts = ‘Notification received date and time’ field - SR05 calculation starts – ‘When Device-Wearer will be at the additional address’ field on SR05 case - when a visit is closed incomplete with on site arrival outside curfew hours or inside black out schedule before Due date = Fail | KPI result as expected | 9 |  | Not Started |  |  |  | STRY0088347
KPSE46 | KPI 9 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - a new or existing Service Request case with subcategory SR04,05,09,10 and calculated KPI 9 Due Date - a work order and work order task exist - a device wearer with existing personal schedule associated - close the WOT (complete and/or incomplete) - SR04,05,09,10, SR09, SR10, calculation starts = ‘Notification received date and time’ field - SR05 calculation starts – ‘When Device-Wearer will be at the additional address’ field on SR05 case - when a visit is closed complete outside of curfew hours and inside black out schedule Before due date= KPI Pass | KPI result as expected | 9 |  | Not Started |  |  |  | STRY0088347
KPSE47 | KPI 9 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - a new or existing Service Request case with subcategory SR04,05,09,10 and calculated KPI 9 Due Date - a work order and work order task exist - a device wearer with existing personal schedule associated - close the WOT (complete and/or incomplete) - SR04,05,09,10, SR09, SR10, calculation starts = ‘Notification received date and time’ field - SR05 calculation starts – ‘When Device-Wearer will be at the additional address’ field on SR05 case - when a visit is closed complete inside of curfew hours and outside black out schedule before due date = KPI Pass | KPI result as expected | 9 |  | Not Started |  |  |  | STRY0088347
KPSE48 | KPI 9 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - a new or existing Service Request case with subcategory SR04,05,09,10 and calculated KPI 9 Due Date - a work order and work order task exist - a device wearer with existing personal schedule associated - close the WOT (complete and/or incomplete) - SR04,05,09,10, SR09, SR10, calculation starts = ‘Notification received date and time’ field - SR05 calculation starts – ‘When Device-Wearer will be at the additional address’ field on SR05 case - when a visit is closed complete outside of curfew hours and inside black out schedule After due date= KPI Fail | KPI result as expected | 9 |  | Not Started |  |  |  | STRY0088347
KPSE49 | KPI 9 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - a new or existing Service Request case with subcategory SR04,05,09,10 and calculated KPI 9 Due Date - a work order and work order task exist - a device wearer with existing personal schedule associated - close the WOT (complete and/or incomplete) - SR04,05,09,10, SR09, SR10, calculation starts = ‘Notification received date and time’ field - SR05 calculation starts – ‘When Device-Wearer will be at the additional address’ field on SR05 case - when a visit is closed complete inside of curfew hours and outside black out schedule After due date = KPI Fail | KPI result as expected | 9 |  | Not Started |  |  |  | STRY0088347
KPSE50 | KPI 9 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - a new or existing Service Request case with subcategory SR04,05,09,10 and calculated KPI 9 Due Date - a work order and work order task exist - a device wearer with existing personal schedule associated - close the WOT (complete and/or incomplete) - SR04,05,09,10, SR09, SR10, calculation starts = ‘Notification received date and time’ field - SR05 calculation starts – ‘When Device-Wearer will be at the additional address’ field on SR05 case - when a visit is closed incomplete outside of curfew hours and inside black out schedule After due date= KPI Fail | KPI result as expected | 9 |  | Not Started |  |  |  | STRY0088347
KPSE51 | KPI 9 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - a new or existing Service Request case with subcategory SR04,05,09,10 and calculated KPI 9 Due Date - a work order and work order task exist - a device wearer with existing personal schedule associated - close the WOT (complete and/or incomplete) - SR04,05,09,10, SR09, SR10, calculation starts = ‘Notification received date and time’ field - SR05 calculation starts – ‘When Device-Wearer will be at the additional address’ field on SR05 case - when a visit is closed incomplete inside of curfew hours and outside black out schedule After due date = KPI Fail | KPI result as expected | 9 |  | Not Started |  |  |  | STRY0088347
KPSE52 | KPI 10 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - an Auto Decommission EMS auto generated case has been created - Auto created by flow when there are LIVE monitoring orders with an "order end" date time that is tomorrow or earlier - the case is associated to a WO with category "Decommission (Collection of assets)" (WOT has the same Work Type) - case is associated to a DW with personal schedule (the field Access Hours on the WOT) - close (complete or incomplete) the WOT - the visit is either closed complete OR Closed Incomplete within curfew hours ON due date ONLY - Verify KPI Pass | KPI result as expected | 7 |  | Not Started |  |  |  | STRY0088348
KPSE53 | KPI 10 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - an Auto Decommission EMS auto generated case has been created - Auto created by flow when there are LIVE monitoring orders with an "order end" date time that is tomorrow or earlier - the case is associated to a WO with category "Decommission (Collection of assets)" (WOT has the same Work Type) - case is associated to a DW with personal schedule (the field Access Hours on the WOT) - close (complete or incomplete) the WOT - the visit is either closed complete OR Closed Incomplete inside or outside Curfew hours before the due date or after due date - Verify KPI Fail | KPI result as expected | 7 |  | Not Started |  |  |  | STRY0088348
KPSE54 | KPI 10 Pass / Fail calculation to include schedules | Pre-requisite data or dependencies: - an Auto Decommission EMS auto generated case has been created - Auto created by flow when there are LIVE monitoring orders with an "order end" date time that is tomorrow or earlier - the case is associated to a WO with category "Decommission (Collection of assets)" (WOT has the same Work Type) - case is associated to a DW with personal schedule (the field Access Hours on the WOT) - close (complete or incomplete) the WOT - the visit is Closed Incomplete outside of Curfew hours on the due date - Verify KPI Fail | KPI result as expected | 7 |  | Not Started |  |  |  | STRY0088348
KPSE55 | KPI 6 Pass / Fail calculation to include schedules | Where the first WOT for an AL02,3,5 case is successful (Closed complete) When the WOT onsite arrival time is within Curfew hours or outside of the Black out schedules and Promoted to enforcement and case resolved before the due date Then the KPI will = Pass | KPI result as expected | 3 |  | Not Started |  |  |  | STRY0088352
KPSE56 | KPI 6 Pass / Fail calculation to include schedules | Where the first WOT for an AL02,3,5 case is successful (Closed complete) When the WOT onsite arrival time is Outside Curfew hours or Inside of the Black out schedules and Promoted to enforcement and case resolved before the due date Then the KPI will = Pass | KPI result as expected | 3 |  | Not Started |  |  |  | STRY0088352
KPSE57 | KPI 6 Pass / Fail calculation to include schedules | Where the first WOT for an AL02,3,5 case is successful (Closed complete) When the WOT onsite arrival time is within / outside Curfew hours or inside / outside of the Black out schedules and NOT Promoted to enforcement and case resolved before the due date Then the KPI will = Fail | KPI result as expected | 3 |  | Not Started |  |  |  | STRY0088352
KPSE58 | KPI 6 Pass / Fail calculation to include schedules | Where the first WOT for an AL02,3,5 case is Unsuccessful (Closed incomplete) When the WOT onsite arrival time is inside / outside Black out schedules or inside / outside of curfew hours and NOT Promoted to enforcement and case resolved before the due date Then the KPI = Fail | KPI result as expected | 3 |  | Not Started |  |  |  | STRY0088352
KPSE59 | KPI 6 Pass / Fail calculation to include schedules | Where the first WOT for an AL02,3,5 case is Unsuccessful (Closed incomplete) When the WOT onsite arrival time is inside Black out schedules or outside of curfew hours and Promoted to enforcement and case resolved before the due date Then the KPI = Fail | KPI result as expected | 3 |  | Not Started |  |  |  | STRY0088352
KPSE60 | KPI 6 Pass / Fail calculation to include schedules | Where the first WOT for an AL02,3,5 case is Unsuccessful (Closed incomplete) When the WOT onsite arrival time is Outside Black out schedules AND Inside of curfew hours and Promoted to enforcement and case resolved before the due date Then the KPI = Pass | KPI result as expected | 3 |  | Not Started |  |  |  | STRY0088352
KPSE61 | KPI 6 Pass / Fail calculation to include schedules | Where the first WOT for an AL02,3,5 case is Unsuccessful (Closed incomplete) NO Onsite arrival time and case resolved = KPI Fail | KPI result as expected | 2 |  | Not Started |  |  |  | STRY0088352
KPSE62 | New dashboard in the KPI 6 report - 6d | Navigate to "Platform Analytics > Library > Dashboards" Find "Performance Monitoring Reports (KPIs)" dashboard and open it up Navigate to the KPI performance dashboard Navigate to the KPI 6 tab Verify that a new report has been added at the bottom called KPI 6d Verify that the new reports label should be "Monitoring Fault Indication (AL19, AL20, AL21, AL22, AL24)" Verify that it displays the same columns as KPI 6a (AL08/10) Verify that report responds to "KPI 6 Head Due Date" dashboard filter changes. | New report available with correct content | 8 |  | Not Started |  |  |  | STRY0088541
KPSE63 | New dashboard in the KPI 6 report - 6d | Navigate to "Monitoring Fault Indication" table in the backend. Click on the context menu and select view "KPI 6d" if the view is not automatically selected. Verify that KPI 6d view present on the table | New view available with correct content | 3 |  | Not Started |  |  |  | STRY0088542
KPSE64 | New dashboard in the KPI 6 report - 6E | Navigate to "Platform Analytics > Library > Dashboards" Find "Performance Monitoring Reports (KPIs)" dashboard and open it up Navigate to the KPI performance dashboard Navigate to the KPI 6 tab Verify that a new report has been added at the bottom called KPI 6e Verify that the new report shows AL27 & 28 (From the Device Maintenance Table) Verify that it displays the same columns as KPI 6a | New report available with correct content | 6 |  | Not Started |  |  |  | STRY0088542
KPSE65 | New dashboard in the KPI 6 report - 6e | Navigate to "Monitoring Fault Indication" table in the backend. Click on the context menu and select view "KPI 6e" if the view is not automatically selected. Verify that KPI 6e view present on the table | New view available with correct content | 3 |  | Not Started |  |  |  | STRY0088542
KPSE66 | KPI 6 dashboard filter update | Open KPIs dashboard and select the KPI 6 tab Change the filter to display different values and verify that the data on the reports change. Verify that both the monitoring fault indication table and the Device Maintenance table will also be included 7 | Filter works as specified | 3 |  | Not Started |  |  |  | STRY0088559
KPSE67 | Ability to determine if a date & time was within Blackout &/ or personalised schedule | Schedule entry steps test DAILY Scenario 1 - Where Repeat Until 2027-01-01 - Check if the time is before the "repeat until" - Check if within the correct time window - Result TRUE - ACCEPTABLE VISIT Scenario 2 - Where Repeat Until NULL - Result ACCEPTABLE VISIT Scenario 3 - Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks if within the correct time window? - Result FALSE - UNACCEPTABLE VISIT | Date and time checks as operate as specified | 7 |  | Not Started |  |  |  | STRY0088799
KPSE68 | Ability to determine if a date & time was within Blackout &/ or personalised schedule | Schedule entry steps test EVERY WEEKDAY (MON-FRI) Scenario 1 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? FRIDAY = TRUE - Check if within the correct time window? TRUE - Result - ACCEPTABLE VISIT Scenario 2 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Check on Date/Days rules apply? FALSE - SUNDAY - Result SKIPPED - UNACCEPTABLE VISIT Scenario 3 Repeat Until 2027-01-01 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Check on Date/Days rules apply? WEDNESDAY = TRUE - Check if within the correct time window? - Result FALSE - UNACCEPTABLE VISIT | Date and time checks as operate as specified | 3 |  | Not Started |  |  |  | STRY0088799
KPSE69 | Ability to determine if a date & time was within Blackout &/ or personalised schedule | Schedule entry steps test EVERY WEEKEND (SAT,SUN) Scenario 1 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Check on Date/Days rules apply? SATURDAY = TRUE - Check if within the correct time window? TRUE - ACCEPTABLE VISIT Scenario 2 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Check Date/Days rules apply? FRIDAY = FALSE - Result - UNACCEPTABLE VISIT Scenario 3 - Where repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Check Date/Days rules apply? SATURDAY = TRUE - Check if within the correct time window? FALSE - Result UNACCEPTABLE VISIT | Date and time checks as operate as specified | 3 |  | Not Started |  |  |  | STRY0088799
KPSE70 | Ability to determine if a date & time was within Blackout &/ or personalised schedule | schedule entry steps test EVERY MON, WED, FRI Scenario 1 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Check Date/Days rules apply? MONDAY = TRUE - Check if within the correct time window? TRUE - Result ACCEPTABLE VISIT Scenario 2 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Check Date/Days rules apply? TUESDAY = FALSE - UNACCEPTABLE VISIT Scenario 3 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? SATURDAY = TRUE - Checks if within the correct time window? FALSE - Result - UNACCEPTABLE VISIT | Date and time checks as operate as specified | 3 |  | Not Started |  |  |  | STRY0088799
KPSE71 | Ability to determine if a date & time was within Blackout &/ or personalised schedule | Schedule entry steps test EVERY TUES, THURS - Scenario 1 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? SATURDAY = TRUE - Checks if within the correct time window? TRUE - Result ACCEPTABLE VISIT Scenario 2 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? TUESDAY = FALSE - Result UNACCEPTABLE VISIT Scenario 3 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? SATURDAY = TRUE - Check if within the correct time window? FALSE - Result UNACCEPTABLE VISIT | Date and time checks as operate as specified | 3 |  | Not Started |  |  |  | STRY0088799
KPSE72 | Ability to determine if a date & time was within Blackout &/ or personalised schedule | Schedule entry steps test WEEKLY (Repeat on days selected MON, TUES, THURS, SUN) - Scenario 1 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? TUESDAY = TRUE - Check if within the correct time window? TRUE - Result ACCEPTABLE VISIT Scenario 2 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? TUESDAY = TRUE - Check if within the correct time window? FALSE - Result UNACCEPTABLE VISIT Scenario 3 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? WEDNESDAY = FALSE - Result UNACCEPTABLE VISIT | Date and time checks as operate as specified | 10 |  | Not Started |  |  |  | STRY0088799
KPSE73 | Ability to determine if a date & time was within Blackout &/ or personalised schedule | Schedule entry steps test MONTHLY (Repeat on DAY OF MONTH 1st) - Scenario 1 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? TUESDAY.1st = TRUE - Check if within the correct time window? TRUE - Result ACCEPTABLE VISIT Scenario 2 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? TUESDAY.1st = TRUE - Check if within the correct time window? FALSE - Result UNACCEPTABLE VISIT Scenario 3 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? 2nd = FALSE - Result UNACCEPTABLE VISIT | Date and time checks as operate as specified | 10 |  | Not Started |  |  |  | STRY0088799
KPSE74 | Ability to determine if a date & time was within Blackout &/ or personalised schedule | Schedule entry steps test MONTHLY (Repeat on DAY OF WEEK 1st MONDAY) Scenario 1 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? MONDAY 5th = TRUE - Check if within the correct time window? TRUE - Result ACCEPTABLE VISIT Scenario 2 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? THURSDAY/1st = FALSE - Result UNACCEPTABLE VISIT Scenario 3 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? MONDAY/12th = FALSE - Result UNACCEPTABLE VISIT Scenario 4 - Where Repeat Until 2027-01-01 - Check time before the "repeat until"? TRUE - Checks on Date/Days rules apply? MONDAY 5th = TRUE - Check if within the correct time window? FALSE - Result UNACCEPTABLE VISIT | Date and time checks as operate as specified | 10 |  | Not Started |  |  |  | STRY0088799
KPSE75 | KPI 6 Head Due date calculation to include schedules | Pre-requisite data or dependencies: - Violation Investigation record exists and a work order is associated to it with a work order task. - The WOT has a personal schedule attached. Test Steps: Create or identify schedule for adult - curfew Verify head and tail due dates will be updated accordingly. Verify Personalised Curfew schedules and Black out schedules will be bought into the Head due date calculation Verify KPI 6 is being calculated correctly for Alerts AL02/AL03/AL05 | KPI6 Head Due Calculation as expected | 4 |  | Not Started |  |  |  | STRY0088799
KPSE76 | KPI 6 Head Due date calculation to include schedules | Pre-requisite data or dependencies: - Violation Investigation record exists and a work order is associated to it with a work order task. - The WOT has a personal schedule attached. Test Steps: Create or identify schedule for adult - blackout Verify head and tail due dates will be updated accordingly. Verify Personalised Curfew schedules and Black out schedules will be bought into the Head due date calculation Verify KPI 6 is being calculated correctly for Alerts AL02/AL03/AL05 | KPI6 Head Due Calculation as expected | 4 |  | Not Started |  |  |  | STRY0088799
KPSE77 | KPI 6 Head Due date calculation to include schedules | Pre-requisite data or dependencies: - Violation Investigation record exists and a work order is associated to it with a work order task. - The WOT has a personal schedule attached. Test Steps: Create or identify schedule for child - curfew Verify head and tail due dates will be updated accordingly. Verify Personalised Curfew schedules and Black out schedules will be bought into the Head due date calculation Verify KPI 6 is being calculated correctly for Alerts AL02/AL03/AL05 | KPI6 Head Due Calculation as expected | 4 |  | Not Started |  |  |  | STRY0088799
KPSE78 | KPI 6 Head Due date calculation to include schedules | Pre-requisite data or dependencies: - Violation Investigation record exists and a work order is associated to it with a work order task. - The WOT has a personal schedule attached. Test Steps: Create or identify schedule for child - blackout Verify head and tail due dates will be updated accordingly. Verify Personalised Curfew schedules and Black out schedules will be bought into the Head due date calculation Verify KPI 6 is being calculated correctly for Alerts AL02/AL03/AL05 | KPI6 Head Due Calculation as expected | 4 |  | Not Started |  |  |  | STRY0088799
KPSE79 | KPI 4 & 5 - to look at Escalated From case | Pre-requisite data or dependencies: - New violation investigation case created or use an existing case that hasn't been resolved. (Escalation) Test Steps: 1. From the violation investigation case, click the ellipsis in the top right of the workspace and click "Promote to Enforcement" 2. A new Non-compliance enforcement case will get created, populate all mandatory fields with relevant information 3. Click the 3 dots in the upper left of the record next to words non-compliance enforcement 4. Click "Show XML" 5. Ctrl + F and find "kpi_", you should find the kpi_4_5_head... in there should be the correct date based on the acceptance criteria 6. The Head / Tail due date calculation will be from the escalated from case created on date and time (6 days if on or before violation period, 7 if after) | KPI result as expected | 6 |  | Not Started |  |  |  | STRY0086767
KPSE80 | KPI 4 & 5 - to look at Escalated From case | Pre-requisite data or dependencies: - New violation investigation case created or use an existing case that hasn't been resolved. (No Escalation) Test Steps: 1. From the violation investigation case, click the ellipsis in the top right of the workspace and click "Promote to Enforcement" 2. A new Non-compliance enforcement case will get created, populate all mandatory fields with relevant information 3. Click the 3 dots in the upper left of the record next to words non-compliance enforcement 4. Click "Show XML" 5. Ctrl + F and find "kpi_", you should find the kpi_4_5_head... in there should be the correct date based on the acceptance criteria 6. Where no escalated from case the Head / tail due date calculation will be from the enforcement case created on date and time | KPI result as expected | 6 |  | Not Started |  |  |  | STRY0086767

## Validation (hidden)
Pass | Open
Fail | Retest
No Run | Ready for Prod
Not Completed | Training
In Progress | Closed
Out of Scope | On Hold
Development
Blocked
Not Started

## Defects
Incident / JIRA ref | Test ID | Issue | Description | Category | Impact Rating (H-M-L) | Date Opened | Date Resolved | Target Release Date | Status | Resolution | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
6.1.25
Note on J1: Barlow, Beverley: Open - Draft, WIP Retest - BAT testing Ready for Prod - retest passed Training - workaround or info for training Closed - test data or raised in error On Hold - in future release

## Sheet1 (hidden)
Testing Timeline
| 19th |  | 20th |  | 21st | 24th | 25th | 26th | 27th | 28th
ST | OE44 * Install alcohol kit | ST | DV50 * Asset Manager BPSS persona | ST | DV50 * Asset Manager BPSS persona
KW | DV41 * Field Service Officer persona | ST | DV51 * Asset Manager CTC persona | ST | DV51 * Asset Manager CTC persona
KW | DV42 * Field Service Officer SPECIALS persona | ST | DV21 * Field Service Scheduler BPSS persona | ST | DV21 * Field Service Scheduler BPSS persona
LJ | DV44 * Quality Assurance CTC persona | ST | DV22 * Field Service Scheduler CTC persona | ST | DV22 * Field Service Scheduler CTC persona
EM | DV48 * CMT Immigration persona FAILED | TL / MHI | TA08 * atv breaches |  | TA31
EM | DV49 * CMT (MoJ) personas PASSED | ST | OEO7 * install following OE01 decom |  | TA10 / OE70
ST | OE69 * install NFD | EM | TA04 *EXCLUSION | EM | TA04 *EXCLUSION
EM | TA09 / OE69 * start the AL18 process | EM | TA30 *AL15 | EM | TA30 *AL15
TL / MHI | TA01 / OE01 * finish generating the atvs & breach packs | EM | TA47 * AL24 -SPOOF | EM | TA47 * AL24 -SPOOF
TL / MHI | TA52 / OE01 * generate AL04 | LJ | TA48 * AL20 |  | OE06
ST | TA43 / OE01 * request spoof event from AUEM | LJ | OE04 * check further visit has generated after previous visit booked off as faulty equipment |  | OE76
ST | OE01 * decom kit once event has been spoofed | ST | OE01 * decom kit |  | OE08
EM / ST & KW | OE04 * Create order * Assign WOT to Mark * 2x no show visits | ST | OE03 * 2x no show |  | TA41
ST & KW | OE03 * Assign WOT to Mark * 2x no show visits | TL / MHI | TA02 * 2x no show breach |  | OE09 | NO SHOW
TL / MHI | TA05 / OE02 * Create multiple exclusions Day 1 | TL / MHI | TA05 / OE02 * Create multiple exclusions Day 2 |  | OE10 | BOOK OFFS
TL / MHI & ST | TA11 / OE02 * Generate strap tamper * Complete tamper visit | TL / MHI | TA46 * breach |  | OE15
TL / MHI | TA33 / OE20 * battery dead | ST | TA03 * 2x no show |  | OE16
MS | OE08 * Create order | TL / MHI | TA03 * breach |  | OE17
MS | OE09 * Create order | ST | OE11 * 2x no show |  | OE12
MS | OE10 * Create order | TL / MHI | TA13 * breach |  | OE13
MS | OE11 * Create order | LJ | TA68 * breach | LJ | TA68 * breach
MS | OE12 * Create order | EM | OE18 * decom
MS | OE13 * Create order | MS | OE15 * create order
CL | OE45 * Create order | MS | OE16 * create order
CL | OE46 * Create order | MS | OE17 * create order
CL | OE47 * Create order | MS | OE19 * create order
ST | OE14 * decom kit | MS | OE21 * create order
ST | OE20 * install kit | MS | OE22 * create order
TL / MHI | TA08 * start atv breaches | MS | OE23 * create order
|  | MS | OE24 * create order
|  | MS | OE25 * create order
|  | MS | OE26 * create order | MS | OE26 * create order
|  | MS | OE27 * create order
|  | MS | OE28 * create order | MS | OE28 * create order
|  | CL | OE29 * create order | MS | OE29 * create order
|  | CL | OE30 * create order | MS | OE30 * create order
|  | CL | OE31 * create order | MS | OE31 * create order
|  | CL | AC01 * create order | CL | AC01 * create order
|  | CL | AC02 * create order | CL | AC02 * create order
|  | CL | AC03 * create order | CL | AC03 * create order
|  | CL | AC04 * create order | CL | AC04 * create order
|  | LJ | DV41 * Field Service Officer persona
|  | LJ | DV42 * Field Service Officer SPECIALS persona
|  | LJ | TA40 * once the 2x no shows are complete - create a new installation work order
|  | ST | TA40 * threatening words & behaviour
|  | LJ | TA40 * breach
|  | TL / MHI | TA58 * aggregation
|  | TL / MHI | TA59 * aggregation
|  | TL / MHI | TA60 * aggregation |  | TA60 * aggregation
|  | TL / MHI | TA61 * aggregation |  | TA61 * aggregation
|  | TL / MHI | TA62 * aggregation |  | TA62 * aggregation
|  | ST | TA46 * 1x threatening words & behaviour
|  | EM | TA46 * breach
|  | LJ | OE49
|  | LJ | OE50

## OVERALL
Test ID | Test Scenario | Test Steps | Outcome Expected | # of Steps | Completed Steps | Status | Notes | Data notes | Tested by | Story
#REF!