## Summary
Release | Story | Traceability | Exec Status | Issue | Planned Tests | Execution Tests | Passed | Failed | In Progress | Not Started | Passed w/ Evidence
RLSE1000001 Extraction Validation | STRY1000001 | 🟢 Tests present | 🟢 Passed with evidence |  | 3 | 3 | 3 | 0 | 0 | 0 | 3
RLSE1000001 Extraction Validation | STRY1000002 | 🟢 Tests present | 🟢 Passed with evidence |  | 3 | 3 | 3 | 0 | 0 | 0 | 3
RLSE1000001 Extraction Validation | STRY1000003 | 🟢 Tests present | 🟢 Passed with evidence |  | 2 | 2 | 2 | 0 | 0 | 0 | 2
RLSE1000002 Audit Validation | STRY2000001 | 🟢 Tests present | 🟢 Passed with evidence |  | 5 | 5 | 5 | 0 | 0 | 0 | 5
RLSE1000002 Audit Validation | STRY2000002 | 🟡 Tests present (not linked) | 🟢 Passed with evidence | Duplicate: AU30 (also in STRY2000004) ¦ Misaligned: AU12 ¦ Extra: AU30 | 3 | 3 | 3 | 0 | 0 | 0 | 3
RLSE1000002 Audit Validation | STRY2000003 | 🟡 Tests present (not linked) | 🟢 Passed with evidence | Misaligned: AU21 | 2 | 1 | 1 | 0 | 0 | 0 | 1
RLSE1000002 Audit Validation | STRY2000004 | 🔴 Tests missing | 🟢 Passed with evidence | Duplicate: AU30 (also in STRY2000002) ¦ Missing: AU31 ¦ Extra: AU21 | 2 | 2 | 2 | 0 | 0 | 0 | 2
RLSE1000002 Audit Validation | STRY2000005 | 🔴 Tests missing | 🔴 Failed tests present | Missing: AU42 ¦ Extra: AU43 ¦ Failed: AU41 ¦ Missing evidence: AU40 | 3 | 3 | 1 | 1 | 0 | 1 | 0

## Traceability Gaps
Release | Story | Source File | Sheet | Planned Tests | Execution Tests | Missing Tests | Misaligned Tests | Extra Tests | Planned Count | Coverage Count | Missing Count | Extra Count | Has Gap
RLSE1000001 Extraction Validation | STRY1000001 | Extraction Validation Test Assurance Scripts v0.3.xlsx | Phase A | EX01, EX02, EX03 | EX01, EX02, EX03 |  |  |  | 3 | 3 | 0 | 0 | FALSE
RLSE1000001 Extraction Validation | STRY1000002 | Extraction Validation Test Assurance Scripts v0.3.xlsx | Phase B | EX10, EX11, EX12 | EX10, EX11, EX12 |  |  |  | 3 | 3 | 0 | 0 | FALSE
RLSE1000001 Extraction Validation | STRY1000003 | Extraction Validation Test Assurance Scripts v0.3.xlsx | Phase B | EX20, EX21 | EX20, EX21 |  |  |  | 2 | 2 | 0 | 0 | FALSE
RLSE1000002 Audit Validation | STRY2000001 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Core | AU01, AU02, AU03, AU04, AU05 | AU01, AU02, AU03, AU04, AU05 |  |  |  | 5 | 5 | 0 | 0 | FALSE
RLSE1000002 Audit Validation | STRY2000002 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | AU10, AU11, AU12 | AU10, AU11, AU30 | AU12 | AU12 | AU30 | 3 | 3 | 1 | 1 | TRUE
RLSE1000002 Audit Validation | STRY2000003 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | AU20, AU21 | AU20 | AU21 | AU21 |  | 2 | 2 | 1 | 0 | TRUE
RLSE1000002 Audit Validation | STRY2000004 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | AU30, AU31 | AU21, AU30 | AU31 |  | AU21 | 2 | 1 | 1 | 1 | TRUE
RLSE1000002 Audit Validation | STRY2000005 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | AU40, AU41, AU42 | AU40, AU41, AU43 | AU42 |  | AU43 | 3 | 2 | 1 | 1 | TRUE

## Missing
MissingTest
AU31
AU42

## Extra
ExtraTest
AU43
TESTID

## Story_To_Test_Map
Story | Test
STRY1000001 | EX01
STRY1000001 | EX02
STRY1000001 | EX03
STRY1000002 | EX10
STRY1000002 | EX11
STRY1000002 | EX12
STRY1000003 | EX20
STRY1000003 | EX21
STRY2000001 | AU01
STRY2000001 | AU02
STRY2000001 | AU03
STRY2000001 | AU04
STRY2000001 | AU05
STRY2000002 | AU10
STRY2000002 | AU11
STRY2000002 | AU12
STRY2000003 | AU20
STRY2000003 | AU21
STRY2000004 | AU30
STRY2000004 | AU31
STRY2000005 | AU40
STRY2000005 | AU41
STRY2000005 | AU42

## Execution_Attachments
Sheet | Row | Story | Test ID | Status | File | Evidence | Test Result
Revised Edge Cases | 2 | STORY | TESTID | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | No | Passed
Revised Edge Cases | 3 | STRY2000002 | AU10 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 4 | STRY2000002 | AU11 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 5 | NEGATIVE | AU12 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 6 | STRY2000003 | AU20 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 7 | STRY2000004 | AU21 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 8 | STRY2000004 | AU30 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 9 | STRY2000002 | AU30 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 10 | STRY2000005 | AU40 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | No | Passed
Revised Edge Cases | 11 | STRY2000005 | AU41 | Failed | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Fail
Revised Edge Cases | 12 | STRY2000005 | AU43 | Not Started | Audit Validation Test Assurance Scripts v0.3.xlsx | No | N/A
Revised Core | 2 | STRY2000001 | AU01 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Core | 3 | STRY2000001 | AU02 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Core | 4 | STRY2000001 | AU03 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Core | 5 | STRY2000001 | AU04 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Core | 6 | STRY2000001 | AU05 | Passed | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase A | 2 | STRY1000001 | EX01 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase A | 3 | STRY1000001 | EX02 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase A | 4 | STRY1000001 | EX03 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase B | 2 | STRY1000002 | EX10 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase B | 3 | STRY1000002 | EX11 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase B | 4 | STRY1000002 | EX12 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase B | 5 | STRY1000003 | EX20 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase B | 6 | STRY1000003 | EX21 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced

## Execution_Detail
Release | Story | Test ID | Exec File | Sheet | Status | Aligned | Execution Location
RLSE1000001 Extraction Validation | STRY1000001 | EX01 | Extraction Validation Test Assurance Scripts v0.3.xlsx | Phase A | Evidenced | YES | STRY1000001
RLSE1000001 Extraction Validation | STRY1000001 | EX02 | Extraction Validation Test Assurance Scripts v0.3.xlsx | Phase A | Evidenced | YES | STRY1000001
RLSE1000001 Extraction Validation | STRY1000001 | EX03 | Extraction Validation Test Assurance Scripts v0.3.xlsx | Phase A | Evidenced | YES | STRY1000001
RLSE1000001 Extraction Validation | STRY1000002 | EX10 | Extraction Validation Test Assurance Scripts v0.3.xlsx | Phase B | Evidenced | YES | STRY1000002
RLSE1000001 Extraction Validation | STRY1000002 | EX11 | Extraction Validation Test Assurance Scripts v0.3.xlsx | Phase B | Evidenced | YES | STRY1000002
RLSE1000001 Extraction Validation | STRY1000002 | EX12 | Extraction Validation Test Assurance Scripts v0.3.xlsx | Phase B | Evidenced | YES | STRY1000002
RLSE1000001 Extraction Validation | STRY1000003 | EX20 | Extraction Validation Test Assurance Scripts v0.3.xlsx | Phase B | Evidenced | YES | STRY1000003
RLSE1000001 Extraction Validation | STRY1000003 | EX21 | Extraction Validation Test Assurance Scripts v0.3.xlsx | Phase B | Evidenced | YES | STRY1000003
RLSE1000002 Audit Validation | STRY2000001 | AU01 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Core | Evidenced | YES | STRY2000001
RLSE1000002 Audit Validation | STRY2000001 | AU02 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Core | Evidenced | YES | STRY2000001
RLSE1000002 Audit Validation | STRY2000001 | AU03 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Core | Evidenced | YES | STRY2000001
RLSE1000002 Audit Validation | STRY2000001 | AU04 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Core | Evidenced | YES | STRY2000001
RLSE1000002 Audit Validation | STRY2000001 | AU05 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Core | Evidenced | YES | STRY2000001
RLSE1000002 Audit Validation | STRY2000002 | AU10 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | Evidenced | YES | STRY2000002
RLSE1000002 Audit Validation | STRY2000002 | AU11 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | Evidenced | YES | STRY2000002
RLSE1000002 Audit Validation | STRY2000002 | AU12 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | Evidenced | NO | NEGATIVE
RLSE1000002 Audit Validation | STRY2000003 | AU20 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | Evidenced | YES | STRY2000003
RLSE1000002 Audit Validation | STRY2000003 | AU21 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | Evidenced | NO | STRY2000004
RLSE1000002 Audit Validation | STRY2000004 | AU30 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | Evidenced | YES | STRY2000004
RLSE1000002 Audit Validation | STRY2000004 | AU30 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | Evidenced | NO | STRY2000002
RLSE1000002 Audit Validation | STRY2000004 | AU31 |  |  | NOT EXECUTED | NO
RLSE1000002 Audit Validation | STRY2000005 | AU40 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | Passed | YES | STRY2000005
RLSE1000002 Audit Validation | STRY2000005 | AU41 | Audit Validation Test Assurance Scripts v0.3.xlsx | Revised Edge Cases | Fail | YES | STRY2000005
RLSE1000002 Audit Validation | STRY2000005 | AU42 |  |  | NOT EXECUTED | NO

## Plan_Raw
StoryCell | RowText | TestCell
STRY1000001 | STRY1000001 Basic extraction of single tests EX01, EX02, EX03 | EX01, EX02, EX03
STRY1000002 | STRY1000002 Multi-sheet extraction EX10, EX11, EX12 | EX10, EX11, EX12
STRY1000003 | STRY1000003 Cross-sheet reuse EX20, EX21 | EX20, EX21
STRY2000001 | STRY2000001 Range expansion validation AU01 – AU05 | AU01 – AU05
STRY2000002 | STRY2000002 Missing tests scenario AU10, AU11, AU12 | AU10, AU11, AU12
STRY2000003 | STRY2000003 Misalignment scenario AU20, AU21 | AU20, AU21
STRY2000004 | STRY2000004 Duplicate / cross-story tests AU30, AU31 | AU30, AU31
STRY2000005 | STRY2000005 Execution Status Handling AU40, AU41, AU42 | AU40, AU41, AU42

## Exec_Raw
Sheet | Row | Story | Test ID | Status | File | Evidence | Test Result
Revised Edge Cases | 2 | STORY | TESTID | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | No | Passed
Revised Edge Cases | 3 | STRY2000002 | AU10 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 4 | STRY2000002 | AU11 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 5 | NEGATIVE | AU12 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 6 | STRY2000003 | AU20 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 7 | STRY2000004 | AU21 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 8 | STRY2000004 | AU30 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 9 | STRY2000002 | AU30 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Edge Cases | 10 | STRY2000005 | AU40 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | No | Passed
Revised Edge Cases | 11 | STRY2000005 | AU41 | Failed | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Fail
Revised Edge Cases | 12 | STRY2000005 | AU43 | Not Started | Audit Validation Test Assurance Scripts v0.3.xlsx | No | N/A
Revised Core | 2 | STRY2000001 | AU01 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Core | 3 | STRY2000001 | AU02 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Core | 4 | STRY2000001 | AU03 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Core | 5 | STRY2000001 | AU04 | Pass | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Revised Core | 6 | STRY2000001 | AU05 | Passed | Audit Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase A | 2 | STRY1000001 | EX01 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase A | 3 | STRY1000001 | EX02 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase A | 4 | STRY1000001 | EX03 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase B | 2 | STRY1000002 | EX10 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase B | 3 | STRY1000002 | EX11 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase B | 4 | STRY1000002 | EX12 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase B | 5 | STRY1000003 | EX20 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced
Phase B | 6 | STRY1000003 | EX21 | Pass | Extraction Validation Test Assurance Scripts v0.3.xlsx | Yes | Evidenced